## Sheet1
Annex 5 Implementation Timetable
Project/Programme Title:
COMPONENTS/OUTPUTS | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025
| Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Component 1
1.1 A Regional Climate Centre established
1.1.1 Design the institutional and organisational framework for the RCC (e.g. admin and logistic responsibilities) | 2021 Q3: Strategic Plan; 2021 Q4: Strategic Plan; 2022 Q1: Institutional and organisational framework consultation; 2022 Q2: Institutional and organisational framework consultation; 2022 Q3: Institutional and organisational framework consultation; 2022 Q4: Institutional and organisational framework signed
1.1.2 Develop a regional climate services strategy for the RCC | 2021 Q3: Strategic Plan; 2021 Q4: Strategic Plan; 2022 Q1: Legal and Regulatory framework consultation; 2022 Q2: Legal and Regulatory framework consultation; 2022 Q3: Legal and Regulatory framework consultation; 2022 Q4: Legal and Regulatory framework consultation; 2023 Q1: Legal and Regulatory framework consultation; 2023 Q2: Climate services strategy signed
1.1.3 Design the regional lab for maintenance and annual calibration of equipment (to be established in Seychelles), and the regional training lab (in Mauritius) strategies (implementation under component 2) | 2021 Q4: Strategic Plan; 2022 Q1: Strategic Plan; 2022 Q2: Legal and Regulatory framework consultation; 2022 Q3: Legal and Regulatory framework consultation; 2022 Q4: Regional Lab and Regional training strategy signed
1.1.4 Prepare a strategy to improve Regional Numerical Weather Prediction | 2021 Q3: Strategic Plan; 2021 Q4: Strategic Plan; 2022 Q1: Legal and Regulatory framework consultation; 2022 Q2: Legal and Regulatory framework consultation; 2022 Q3: Legal and Regulatory framework consultation; 2022 Q4: Legal and Regulatory framework consultation; 2023 Q1: Legal and Regulatory framework consultation; 2023 Q2: NWP strategy signed
1.1.5 Design a communication strategy to disseminate relevant information on the Regional User Interface Platform (UIP) linked to the RCC | 2021 Q3: Strategic Plan; 2021 Q4: Strategic Plan; 2022 Q1: Legal and Regulatory framework consultation; 2022 Q2: Legal and Regulatory framework consultation; 2022 Q3: Communication strategy signed
1.2 Improved staffing of the RCC and national met. Services
1.2.1 Train new recruit | 2021 Q3: Training Plan; 2021 Q4: Training Plan; 2022 Q1: Initial training for technicians and engineers for two and three years respectively; 2024 Q1: Initial training for technicians and engineers for two and three years respectively
1.2.2 Update training for existing staff |  |  | Training Plan | Training Plan |  |  | Information managment workshop | Analysis workshop | GIS workshop | Remote sensing workshop | Information managment workshop | Analysis workshop | GIS workshop | Remote sensing workshop | Information managment workshop | Analysis workshop | GIS workshop | Remote sensing workshop
1.3 Institutional arrangements and operational strategy of national met. services strengthened
1.3.1 Develop and implement a plan to strengthen institutional settings of NHMSs | 2021 Q3: Strategic Plan; 2021 Q4: Strategic Plan; 2022 Q1: Legal and Regulatory framework consultation; 2022 Q2: Legal and Regulatory framework consultation; 2022 Q3: Legal and Regulatory framework consultation; 2022 Q4: Legal and Regulatory framework consultation; 2023 Q1: Legal and Regulatory framework consultation; 2023 Q2: Legal and Regulatory framework consultation; 2023 Q3: First SOP operational with the other institutions; 2024 Q2: Second SOP operational; 2025 Q1: Third SOP operational
1.3.2 Develop a business plan for each NHMS | 2021 Q3: Strategic Plan; 2021 Q4: Strategic Plan; 2022 Q1: Legal and Regulatory framework consultation; 2022 Q2: Legal and Regulatory framework consultation; 2022 Q3: Legal and Regulatory framework consultation; 2022 Q4: Legal and Regulatory framework consultation; 2023 Q1: Legal and Regulatory framework consultation; 2023 Q2: Business plans signed
1.3.3 Design the transition support plan | 2021 Q3: Strategic Plan; 2021 Q4: Strategic Plan; 2022 Q1: Internal and Regulatory framework consultation; 2022 Q2: Internal and Regulatory framework consultation; 2022 Q3: Internal and Regulatory framework consultation; 2022 Q4: Internal and Regulatory framework consultation; 2023 Q1: Internal and Regulatory framework consultation; 2023 Q2: Transition support plan signed
1.3.4 Develop and support implementation of the NFCS | 2021 Q3: Strategic Plan; 2021 Q4: Strategic Plan; 2022 Q1: Legal and Regulatory framework consultation; 2022 Q2: Legal and Regulatory framework consultation; 2022 Q3: Legal and Regulatory framework consultation; 2022 Q4: Legal and Regulatory framework consultation; 2023 Q1: Legal and Regulatory framework consultation; 2023 Q2: NFCS signed
1.4 Detailed Design, technical specification, system integration and tendering process of Project Activities
1.4.1. Produce a detailed design and system integration for each met service |  | NMHSs systems design | NMHSs systems design | Support implementation | Support implementation | Support implementation | Support implementation | Support implementation | Support implementation | Support implementation | Support implementation | Support implementation | Support implementation | Support implementation | Support implementation | Support implementation | Support implementation | Support implemen-tation | Support implementation | Support implementation
1.4.2 Develop a system integration at hydromet production level and at end users’ level to have a value chain integration for climatic services and alert |  | NMHS systems integration plan | NMHS systems integration plan | NMHS systems integration plan | NMHS systems integration plan | NMHS systems integration plan | NMHS systems integration plan | Support implementation | Support implementation | Support implementation | Support implementation | Support implementation | Support implementation | Support implementation | Support implementation | Support implementation | Support implementation | Support implemen-tation | Support implementation | Support implementation
Component 2
2.1 Enhanced hydro-meteorological observing, monitoring, and impact forecasting services
2.1.1 Modernise/upgrade climate observation and monitoring network |  |  |  | Procurement of hardware | Procurement of hardware | Procurement of hardware | Installation | Installation | Installation | Support | Support | Support | Support | Support | Support | Support | Support | Support | Support | Support
2.1.2 Modernise/upgrade information system for telecom, forecast, climatology |  |  |  | Procurement of software | Procurement of software | Procurement of software | Installation | Installation | Installation | Support | Support | Support | Support | Support | Support | Support | Support | Support | Support | Support
2.2 Regional facilities for maintenance and training established
2.2.1 Establish maintenance lab in Seychelles | [7 empty] | Procurement of hardware | Procurement of hardware | Installation | Installation | Support | Support | Support | Support | Support | Support | Support | Support | Support
2.2.2 Refurbish regional training centre of Mauritius to train observers and forecasters | [7 empty] | Procurement of hardware and software | Procurement of hardware and software | Installation | Installation | Support | Support | Support | Support | Support | Support | Support | Support | Support
2.3 R&D capacities enhanced to improve understanding of climate and disaster risks on communities and sectors
2.3.1 Organise training and R&D activities to improve meteorological and climate modelling capacity and hydraulic modelling for flood prevision (i.e. flood-prone area mapping and flood propagation model) | 2021 Q3: Training Plan; 2021 Q4: Training Plan; 2022 Q1: Specific R&D training for engineers for one year; 2023 Q1: Specific R&D training for engineers for one year; 2024 Q1: Specific R&D training for engineers for one year; 2025 Q1: Specific R&D training for engineers for one year
2.3.2 Develop climate-related hazards maps for key hazards, including heavy rainfall/floods (can be linked to cyclones), storm surges, marine inundation and coastal erosion | 2021 Q2: Strategic Plan; 2021 Q3: Strategic Plan; 2021 Q4: Development of climate hazards maps; 2022 Q1: Development of climate hazards maps; 2022 Q2: Development of climate hazards maps; 2022 Q3: Development of climate hazards maps; 2023 Q3: Maps update; 2024 Q3: Maps update; 2025 Q3: Maps update
2.3.3 Develop climate-risk vulnerability maps based on the climate hazard maps | 2021 Q2: Strategic Plan; 2021 Q3: Strategic Plan; 2022 Q2: Development of climate risk vulnerabilitymaps; 2022 Q3: Development of climate risk vulnerabilitymaps; 2022 Q4: Development of climate risk vulnerabilitymaps; 2023 Q1: Development of climate risk vulnerabilitymaps; 2023 Q4: Maps update; 2024 Q4: Maps update; 2025 Q4: Maps update
Component 3
3.1 Climate services improved based on end-users needs
3.1.1 Produce and/or update long term climate services responding to the needs of each country | 2021 Q2: End_user needs; 2021 Q3: Prototype of services; 2022 Q1: Operational services batch 1; 2022 Q4: User feedback Workshop; 2023 Q1: Operational services batch 2; 2024 Q1: User feedback Workshop; 2024 Q2: Operational services batch 3; 2025 Q2: User feedback Workshop; 2025 Q3: Improvment of services; 2025 Q4: Improvment of services
3.1.2 Improve emergency response for on-the-ground interventions (during/after key hazards) | 2021 Q3: Risk assessments; 2021 Q4: Risk assessments; 2022 Q3: Response action plan; 2023 Q1: Operational procedures effective; 2023 Q4: Update of plan; 2024 Q4: Update of plan
3.1.3 Develop Project/Funding Proposals | 2023 Q4: Strategic plan; 2024 Q1: Development of project proposal; 2024 Q2: Development of project proposal; 2024 Q3: Development of project proposal
3.2 Communication of CS improved
3.2.1 Train the producers of climate forecasts on how to package information in a user-friendly way | 2021 Q3: Training Plan; 2021 Q4: Training Plan; 2022 Q1: Initial training for two or three months; 2023 Q1: Update of the training; 2024 Q1: Update of the training; 2025 Q1: Update of the training
3.2.2 Strengthen early warning dissemination for key sectors/general public | 2022 Q1: Strategic planning; 2022 Q2: Strategic planning; 2022 Q3: User sensitization; 2022 Q4: User sensitization; 2023 Q1: User sensitization; 2023 Q3: User sensitization; 2023 Q4: User sensitization; 2024 Q1: User sensitization; 2024 Q3: User sensitization; 2024 Q4: User sensitization; 2025 Q1: User sensitization
3.3 Communication platforms for end-users and providers of CS established
3.3.1 Establish and sensitise CS user groups | 2022 Q2: Strategic planning; 2022 Q3: Strategic planning; 2022 Q4: User sensitization; 2023 Q1: User sensitization; 2023 Q2: User sensitization; 2023 Q4: User sensitization; 2024 Q1: User sensitization; 2024 Q2: User sensitization; 2024 Q4: User sensitization; 2025 Q1: User sensitization; 2025 Q2: User sensitization
3.3.2 Strengthen the User Interface Platform (UIP) |  | Technical study | Procurement of software for NMHS | Procurement of software for NMHS | Procurement of software for NMHS | Procurement of software for NMHS | Prototype of services |  | Operational services batch 1 |  | User feedback Workshop | Operational services batch 2 |  | User feedback Workshop | Operational services batch 3 |  |  | User feedback Workshop | Improvment of services
3.3.3 Support SWIOCOF to ensure the active participation of climate services users | 2021 Q3: SWIOCOF organization; 2022 Q3: SWIOCOF organization; 2023 Q3: SWIOCOF organization; 2024 Q3: SWIOCOF organization; 2025 Q2: Strategy to perennise SWIOCOF; 2025 Q3: SWIOCOF organization
Project Monitoring* | 2021 Q2: Inception Report; 2022 Q1: APR; 2023 Q1: APR; 2023 Q3: Interim Evaluation; 2024 Q1: APR; 2025 Q1: Completion Report; 2025 Q4: Final Evaluation
APR = Annual Performance Report
*In addition to this monitoring requirements, the Funded Activity is also subject to financial reporting per the AMA/FAA, such as Unaudited/Audited Financial Statements, Financial information reports, and other reports as defined in the FAA.