| Project/Programme title: | Building Regional Resilience through Strengthened Meteorological, Hydrological and Climate Services in the Indian Ocean Commission (IOC) Member Countries |
| --- | --- |
| Country(ies): | Comoros, Madagascar, Mauritius and Seychelles |
| Accredited Entity: | French Development Agency (AFD) |
| Date of first submission: | [2020/01/23] |
| Date of current submission | [2020/01/23] |
| Version number | [V.001] |

Contents

Section A	PROJECT / PROGRAMME SUMMARY

Section B	PROJECT / PROGRAMME INFORMATION

Section C	FINANCING INFORMATION

Section D	EXPECTED PERFORMANCE AGAINST INVESTMENT CRITERIA

Section E	LOGICAL FRAMEWORK

Section F	RISK ASSESSMENT AND MANAGEMENT

Section G	GCF POLICIES AND STANDARDS

Section H	ANNEXES

Note to Accredited Entities on the use of the funding proposal template

- Accredited Entities should provide summary information in the proposal with cross-reference to annexes such as feasibility studies, gender action plan, term sheet, etc. - Accredited Entities should ensure that annexes provided are consistent with the details provided in the funding proposal. Updates to the funding proposal and/or annexes must be reflected in all relevant documents. - The total number of pages for the funding proposal (excluding annexes) should not exceed 60. Proposals exceeding the prescribed length will not be assessed within the usual service standard time. - The recommended font is Arial, size 11. - Under the GCF Information Disclosure Policy, project and programme funding proposals will be disclosed on the GCF website, simultaneous with the submission to the Board, subject to the redaction of any information that may not be disclosed pursuant to the IDP. Accredited Entities are asked to fill out information on disclosure in section G.4.

Please submit the completed proposal to:

fundingproposal@gcfund.org

Please use the following name convention for the file name:

“FP-[Accredited Entity Short Name]-[Country/Region]-[YYYY/MM/DD]”

| # PROJECT/PROGRAMME SUMMARY |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| A.1. Project or programme | Project | A.2. Public or private sector |  | Public |  |  |  |
| A.3. Request for Proposals (RFP) | Not applicable |  |  |  |  |  |  |
| A.4. Result area(s) |  |  |  |  |  |
|  | Mitigation: Reduced emissions from: ☐ Energy access and power generation: ☐ Low-emission transport: ☐ Buildings, cities, industries and appliances: ☐ Forestry and land use: Adaptation: Increased resilience of: ☒ Most vulnerable people, communities and regions: ☒ Health and well-being, and food and water security: ☐ Infrastructure and built environment: ☐ Ecosystem and ecosystem services: |  |  |  | GCF contribution: Enter number% Enter number% Enter number% Enter number% 50% 50% Enter number% Enter number% |
| A.5. Expected mitigation impact | Not applicable | A.6. Expected adaptation impact |  | 6,054,909 direct beneficiaries; 13,398,377 indirect beneficiaries |  |
|  |  |  |  | 66,5% of countries population is direct and indirect beneficiaries |  |
| A.7. Total financing (GCF + co-finance) | 78 060 500 USD | A.9. Project size |  | Medium (Upto USD 250 million) |  |
| A.8. Total GCF funding requested | 59 592 500 USD |  |  |  |  |
| A.10. Financial instrument(s) requested for the GCF funding | Mark all that apply and provide total amounts. The sum of all total amounts should be consistent with A.8. |  |  |  |  |
|  | ☒ Grant 59 592 500 USD ☐ Loan Enter number ☐ Guarantee Enter number |  | ☐ Equity Enter number ☐ Results-based payment Enter number |  |  |
| A.11. Implementation period | 5 years | A.12. Total lifespan |  | 50 years |  |
| A.13. Expected date of AE internal approval | April 2020 | A.14. ESS category |  | B |  |
| A.15. Has this FP been submitted as a CN before? | Yes ☒ No ☐ | A.16. Has Readiness or PPF support been used to prepare this FP? |  | Yes ☐ No ☒ |  |
| A.17. Is this FP included in the entity work programme? | Yes ☒ No ☐ | A.18. Is this FP included in the country programme? |  | Yes ☐ No ☒ |  |
| A.19. Complementarity and coherence | Yes ☒ No ☐ |  |  |  |  |
| A.20. Executing Entity information | Indian Ocean Commission, intergovernmental organization created in 1984 with the Victoria Agreement. Headquarters agreement signed with Mauritius. |  |  |  |  |
| A.21. Executive summary (max. 750 words, approximately 1.5 pages) |  |  |  |  |  |
| The Global Risk Report (2019) indicates that extreme weather events are amongst the risks with highest impact of the global risk landscape. Among these extreme events, meteorological and hydrological hazards jointly cause more economic damages and loss of life than other disasters. Such hazards are increasing both in frequency and intensity in the South West Indian Ocean region (SWIO region),. Within this region, floods induced by rainfalls from tropical cyclones and non-tropical cyclones are the most frequent catastrophic hazard. The number of affected people – estimated at 14.4 million for the 1964–2014 period – and the physical damages associated to climate-related hazards in Comoros, Madagascar, Mauritius and Seychelles - estimated at USD 13.1 billion over the same period – are expected to further increase in the context of climate change. The IPCC AR5 (2014) indicates with high confidence that current and future climate-related drivers of risks for small islands – including Comoros, Mauritius and Seychelles – during the 21st century include sea level rise, tropical and extratropical cyclones, increasing air and sea surface temperatures, and changing rainfall patterns. Likewise, climate change in Madagascar induces more frequent droughts and floods, sea level rise and increasing temperature, which also have increasing impacts on livelihood, food security, economic development and infrastructure. In this context, there is a need to shift the paradigm towards improved weather, climate, and hydrological services (“Hydromet services”) in the SWIO region to increase weather and climate resilience. The proposed project will support this paradigm shift in the target region where the Hydromet value chain is not well developed and the National Meteorological and Hydrological Services (NMHSs) are facing serious challenges in responding to increasing societal and economic demands, in particular as climate-induced risks shift with climate change. More specifically, the project will support the production of high-quality impact-based climate products and services (CP-CS), including early warning systems (EWS), at the regional and national level. CP-CS, like EWS, support the reduction of climate-induced risks and vulnerability by equipping decision-makers, climate-sensitive sectors and communities with essential information to avoid, mitigate and adapt to the impacts of climate extremes, climate variability and climate change. For example, the latest IPCC report (SROCC 2019) indicates that EWS are low cost and highly cost-efficient when it comes to coastal zones and tackling sea level rise. However, CP-CS in Africa are not well developed and the wider region “has the least developed weather, climate and hydrology observation network, with only 1/8 of the required density and less than 300 weather stations that meet the World Meteorological Organisation (WMO) observation standards”. The proposed Hydromet project is designed to bolster climate resilience among communities by reinforcing NMHS, through strengthening national and regional institutional CP-CS frameworks, fostering regional cooperation and expanding climate knowledge sharing. The regional approach is key to underpin improvements in the production and dissemination of CP-CS, as the four target countries are vulnerable to similar climate-related risks and changes. The Indian Ocean Commission (IOC) is the relevant regional institution covering Comoros, Madagascar, Mauritius and Seychelles to enable enhanced regional cooperation and knowledge sharing with a view to reduce climate-related vulnerability; this institution, the only one to bring together countries of the SWIO region, launched the design process of the proposed Hydromet project, through various consultations with the beneficiary countries to define the project’s outline, and through validation of all project interventions with relevant national stakeholders. The project will deliver: Enhanced institutional capacities and regional cooperation to produce high-quality CP-CS: both national and regional improvements will be achieved through appropriate frameworks and enabling environments. Regional and national Frameworks for Climate Services (RFCS) will be developed and a Regional Climate Centre (RCC) strategy and action plan will be defined by the IOC and its member states; the establishment of the RCC will support synergies, complementarities, regional integration and cost-efficiency gains to produce CP-CS in the SWIO region. This will enable improved climate risks and climate change impact forecasting and management at regional and national levels. At the national level, NMHS staff will receive core trainings on climate risks and management; the operational structure and financial efficiency of their institution will be enhanced. High-quality climate-related data and climate risk assessments: the technical expertise of NMHS staff on observations and monitoring, climate change modelling, data management, ICT and forecasting will be enhanced through training. Moreover, hydro-meteorological data collection infrastructure, management and information systems will be modernised, with a view to improve risk prediction among the four target countries. Training and capacity building to downscale climate change projections in each country will be implemented to enhance understanding of climate change impacts on development processes and key economic sectors for the four target countries. Given the countries’ exposure to floods, specific training on hydrology will be provided; likewise, given the significance of agriculture, fisheries and tourism sectors for the four target countries, training to provide specific user-centered impact-based weather advisories for these sectors will be provided. Improved data on climate change will enable more accurate climate change impact assessment on key sectors via the production of hazard and vulnerability maps and thus support adaptation planning. Enhanced use of climate services for climate change adaptation and disaster risk reduction: CP-CS – including daily weather forecasts, downscaled agricultural weather advisories, risk management and climate change adaptation plans and EWS – will be co-developed, based on the enhanced expertise and high-quality data supported by the project, and in a participatory way between producers and users of CP-CS. These services will especially target key sectors underpinning the economy of the four target countries, namely agriculture, fisheries and tourism. These sectors are highly vulnerable to climate change impacts, but key to support the livelihoods of the vast majority of the population in the SWIO region. Producers and users of climate services will work together to develop high-quality products to ensure they are packaged according to end-user needs, use the most efficient dissemination channels for end-users, and capture user feedback to improve communications processes and products. The proposed Hydromet interventions have been designed to support a cost-effective and locally-appropriate modernisation of NMHS, services and equipment. Key sectors have been selected based on in-country consultations, and relevance in terms of reducing vulnerability to climate change. Climate change impacts will be mainstreamed into CP-CS not only to reduce impacts of climate-related risks, but also to ensure enhanced climate change resilience of the population in Comoros, Madagascar, Mauritius and Seychelles. The proposed project will also enable sustained economic growth in key sectors. Through sector-target interventions, 21% of the population in the four countries (about 6 million people) will benefit directly from the project. |  |  |  |  |  |  |

# PROJECT/PROGRAMME INFORMATION

B.1. Climate context (max. 1000 words, approximately 2 pages)

Baseline of climate vulnerabilities and impacts Comoros, Madagascar, Mauritius and Seychelles, located in the SWIO region, are extremely vulnerable to natural hazards and climate change, especially tropical cyclones and heavy rainfalls, leading to floods, flash floods and landslides, droughts, increased temperatures, and sea level rise. Tropical cyclones (TC) are the most frequent catastrophic hazards in the SWIO region and have been responsible for significant historical economic losses and casualties. Scientific data confirms shifts in the climate patterns observed in the SWIO region, including more floods and droughts based on a comparison of periods 1961-1990 and 1991-2016, as well as increased temperature. Climate change will increase the frequency and/or intensity of climate-related hazards and extremes in the SWIO region such as storms, heavy rainfall events and violent winds. See Annex 2 for details on climate change impacts and vulnerability in the SWIO region. Related threats to livelihoods and economic growth in these island countries are increasing, exacerbating the baseline situation as detailed in Annex 2. Regional and National Climate Change Adaptation Strategies governments of Comoros, Madagascar, Mauritius and Seychelles countries are committed to initiate and support climate-resilient interventions that reduce the vulnerability of their country and population to climate change impacts. This commitment is reflected in several policies, strategies, programmes and projects pertaining to climate change adaptation and climate services All four countries have adopted the Nationally Determined Contributions (NDCs); Comoros and Madagascar have submitted their National Adaptation Programmes of Action (NAPA). All countries, except Seychelles, are in the process of developing their National Adaptation Plan (NAPs). Other relevant domestic policies include Comoros’ national Strategic Plan 2017-2020, Madagascar’s National Climate Change Management Policy (NCCMP, 2012), Mauritius’ National Climate Change Adaptation Policy Framework (2012), and Seychelles’ National Climate Change Strategy (2009) and the Climate Change Policy (currently under development). See Annex 2 for details on existing policies. Because of the regional nature of climate extremes such as cyclones, of their shared vulnerability to climate and climate change-related hazards such as floods and landslides, and of their recognition for the need to strengthen forecasting and climate adaptation in their respective countries, Comoros, Madagascar, Mauritius and Seychelles have adopted the IOC strategy: « Document cadre pour la stratégie régionale d’adaptation au changement climatique des pays membres de la Commission de l’océan Indien 2012-2020 ». This strategy, coordinated by IOC, provides the guideline to foster climate change adaptation in the SWIO region. In particular it recommends enhancing regional coordination, risk forecasting and knowledge exchange for climate change resilience. IOC also takes the lead to organise the SWIO-COF and disseminates seasonal outlooks through a Regional Climate Portal. Hence, IOC is a key institution to initiate and enhance synergies and collaboration for climate-related risks monitoring and risk mitigation strategies in the SWIO region. Scaling up on past and ongoing initiatives and projects The regional Hydromet project will build on, scale up, and complement past and ongoing regional and national projects. To ensure complementarity and identify synergies with existing projects, several meetings were conducted with developments partners such as UNDP, WB, JICA, EU in the four target countries, which are strongly involved in the region and specifically on developing Hydromet projects. Some of these projects are listed below; full list of relevant projects is developed in Annex 2 with full synergies described. - Building Resilience in the Indian Ocean (BRIO) to develop high-resolution climate projections that will extend up to 2100 and reveal long-term trends in temperature, rainfall, and cyclonic activity, 2018-2020, AFD - Ensuring climate resilient water supplies in the Comoros Islands, 2018-2026, UNDP/GCF - Projet d’Amélioration des Capacités d’Adaptation et de Résilience des Communes Rurales face aux Changements Climatiques (PACARC), 2016-2021, PNUD/ FEM - Adaptation des chaînes de valeur agricoles au changement climatique (PrAda), 2017-2022, GIZ - Mauritius Land Drainage Master Plan, AFD - Doppler radar and capacity building 2018-2020, JICA - Seychelles Water & Sanitation Project (SWSP), 2008-2020, AFD/EIB/AWF and Government of Seychelles - Seychelles Monitoring of Algal Bloom, IAEA, Seychelles AFD, the accredited entity for the proposed project, is also taking part in the Africa Hydromet program and is in continuous liaison with World Bank team and other partners. Moreover, the SWIO Hydromet project is designed to be in line with the commitments of the Global Alliance for Hydromet (GAH), endorsed by the GCF during COP25, and thus this proposed project aims to be one of the pioneer projects to be implemented under this new initiative. Finally, the WMO was involved during the feasibility study drafting and approval by beneficiary countries. As a result of this fruitful coordination, the regional component of the WHYCOS program, developed in 2019 by WMO, is included as part of the proposed project to avoid duplication. Addressing current gaps and barriers While the ongoing projects and initiatives are often focused on one specific sector, a country and/or a limited area of intervention within a country, the Hydromet project proposes a regional integrated approach to monitor climate-related risks, produce and disseminate forecasts and warnings. This regional approach, initiated by the IOC and as executing entity for the project, underpins successful, cost-efficient climate risk mitigation and climate change adaptation in the SWIO region. By adopting a regional approach to risk reduction and adaptation, by targeting various sectors – from agriculture, fishing, and tourism – and building upon or scaling up other projects and initiatives, the Hydromet project will trial an innovative regional approach to improve climate resilience in the SWIO region; the success of a regional approach to monitor and manage climate variability and change, thereby improving the region’s socio-economic development, has been demonstrated in other regions of the world, i.e. the Caribbean region.

B.2. Theory of change (max. 1000 words, approximately 2 pages plus diagram)

Through GCF support, the proposed project will overcome key barriers to increasing the climate change resilience of communities by bridging and front-loading the investment gaps on the hydromet services in the region. Business-as-usual Hydromet projects (small-scale, without user-centered approaches) do not allow full resilience and risk-informed sustainable development and economic growth. Without the leverage of the GCF, Comoros, Madagascar, Mauritius and Seychelles will be and remain increasingly hampered by climate-related risks and changes; community livelihoods will be continuously threatened by changes in temperature and rainfall, as well as the increased frequency and intensity of climate extremes. To overcome the barriers to provide timely, accurate, and user-friendly climate services, interventions with the most transformative impact on reducing disaster risk and will foster adaptation to climate change, have been identified based on extensive in-country consultations in the four target countries. These interventions (see section B.3) will support the strengthening of NMHSs to produce targeted, impact-based forecasts (IBF), and the timely dissemination of accurate and high-quality CP-CS, including multi-hazard early warnings (MHEW). The activities will also enhance regional cooperation and knowledge sharing between Comoros, Madagascar, Mauritius and Seychelles, facilitated by the IOC acting as executing entity for this project. IOC’s historical role in the SWIO region (created 36 years ago by SWIO region countries) and core experience in climate monitoring for the region (supporting several projects such as BRIO and Indian Ocean Data Rescue Project) makes the commission the most appropriate institution to gather the SWIO countries within the proposed Hydromet project. The Hydromet project is built around three components to be implemented at both regional and national levels. Component 1: Capacity building, institutional development and regional cooperation Component 2: High-quality climate-related data, improved climate risk assessments and climate change projections Component 3: Enhanced use of climate services for climate change adaptation and disaster risk reduction Figure 1: Theory of Change for Hydromet project - The Baseline problems and climate change issues are developed under Section B.1. - Barriers in the value chain of Hydromet Services to climate change adaptation At the regional level, IOC and its member countries do not have a regional framework and facilities to harmonise risk monitoring and forecasting processes, collaborate and synergise efforts for climate risk prediction, downscale climate change impacts from the regional to the national level, and share risk-related information and risk management experience. At national level, the NMHS of these four countries have limited institutional, financial and technical capacities to monitor climate and weather data, and to produce locally-relevant forecasts to inform decision-making processes (see Annex 2). This is particularly the case in Comoros and Madagascar due to the limited number of surface and upper air stations. Institutional weaknesses have also been noted in the NMHS of the four countries along with limited staffing, as indicated in Annexe 2. As a result, there is limited production and timely dissemination of user-centred climate services including impact-based forecasts (IBF) and EWS that can help reduce risk exposure and vulnerability among communities and economic sectors; this is further exacerbated by a lack of updated climate change projections downscaled at the level of each country. Finally, there are limited interactions between the producers and users of weather and climate services, and therefore limited feedback loops to ensure the production of relevant, high-quality and accurate climate services. The financial resources to overcome these barriers are also not sufficient or not available within the IOC and the concerned countries, because of their LDC/SIDS status and climate change-related threats on their economy, highly dependent on climate-sensitive sectors. Project activities to overcome barriers and catalyse transformational change The three components are designed to achieve the paradigm shift of improved monitoring and improved management of climate, weather and hydrological risks in the short-, medium-, and long-term, that will facilitate growth in key climate sensitive targeted sectors (agriculture, fishing and tourism), and enable resilience and adaptation to climate change impacts. This project provides an opportunity for countries to leverage each other’s strengths, deploy complementary fields of expertise and risk management capacity, and capitalise on successful regional and national initiatives. The regional scope of this project, fostered by IOC, underpins its success to improve climate risk prediction, and promote climate-resilient socio-economic growth in the long-term. The IOC is the only regional institution created and financed by island states of the South-West Indian Ocean Region; it already leads regional initiatives for climate risk management (see Section B. 1). Through its regional status, IOC will champion increased collaboration among the target countries for climate-related risk monitoring. The proposed project impact will be achieved through a mutually-reinforcing integrated approach. Improvement of climate services delivery (Component 3) can only be achieved if supported by appropriate institutional strengthening and regional collaboration and experience exchange (Component 1) and acquisition of specialised equipment and expertise (Component 2). Through Component 1, regional cooperation will be strengthened through establishing a RCC, whose mandate, organisation and facilities will be shared among IOC member countries based on the RCC strategy and a RFCS. Institutional strengthening, including the development of nationally-appropriate business models for meteorological services – will also be implemented in the four target countries to support robust NMHS institutions, ensure financial returns and retain skilled staff. Through Component 2, hydro-meteorological systems and equipment will be modernised to support enhanced monitoring of weather, climate and hydrological risks, and to increase understanding of climate change impacts on the region/ countries and of climate-related hazards and vulnerability. The maintenance and calibration of this equipment will be facilitated and optimized by establishing a regional maintenance and calibration laboratory, as part of the RCC, while training and R&D activities to better understand and forecast climate-related risks will be organised within the regional facilities. Finally, through Component 3, the co-production of accurate CP-CS with their users and end-users in vulnerable sectors and communities, including IBF and EW, and their timely dissemination using appropriate communication means will be fostered; communication between users and producers of CP-CS – including a feedback loop from users to producers on the CP-CS – will also be enhanced and sustained through the User Interface Platform (UIP) and SWIOCOF. Taking advantage of these improvements in the production and dissemination of CP-CS, the four NMHS will more systematically and efficiently consider needs of CP-CS users and end-users to develop targeted products for an increasing number of sectors. This will: i) promote the generation and use of climate information in decision making; ii) strengthen adaptive capacity and reduce exposure to climate risks; and iii) strengthen awareness of climate threats and risk reduction processes within the SWIO region. As a result, these components will support the paradigm shift towards resilient states, institutions, economies, populations and livelihoods to climate-related hazards and to achieve risk-informed sustainable development. Please refer to Annex 2 for details on the project components and their alignment with WMO-GFCS.

B.3. Project/programme description (max. 2000 words, approximately 4 pages)

- Project development objective and contribution to climate change adaptation The project objective is to strengthen adaptive capacity and climate resilience of the vulnerable community and economic sectors of Comoros, Madagascar, Mauritius and Seychelles. This will be achieved through improvement and modernisation of hydro-meteorological systems and services, which will equip users with timely, adequate information to prevent, mitigate and adapt to climate-related hazards and change. Improving CP-CS contributes to climate change adaptation and disaster risk reduction. Indeed, these services enable risk anticipation, emergency response and adaptation planning; by providing decision-makers in climate-sensitive sectors with the needed and required information (see Annex 2). As such, the benefits of the proposed project will support the implementation of NDCs, national adaptation and disaster risk reduction plans, and Sendai targets. The proposed interventions will contribute to achieve the GCF fund-level impact A1.0 Increased resilience and enhanced livelihoods of the most vulnerable people, communities and regions and A2.0 Increased resilience of health and well-being, and food and water security. For example, more accurate, locally-relevant weather forecasts, produced under the proposed project, will facilitate agricultural planning and adjustment to agriculture calendars; weather forecasts will also facilitate risk prevention measures; and timely early warnings will enable the protection of lives, buildings, fisheries, tourism or agricultural equipment and harvests, among other assets. Several GCF outcomes for adaptation will also be achieved through the proposed project, namely: A5.0 Strengthened institutional and regulatory systems for climate-responsive planning and development A6.0 Increased generation and use of climate information in decision-making A7.0 Strengthened adaptive capacity and reduced exposure to climate risks A8.0 Strengthened awareness of climate threats and risk-reduction processes Scope of the project and description The proposed Hydromet project is designed to scale up current initiatives supporting climate services in Comoros, Madagascar, Mauritius and Seychelles. This will be achieved by building on these investments to: - Improve weather and climate monitoring techniques and downscale climate change projections, while complementing existing weather station network or planned hydrological networks, - Enhance the production and dissemination of climate services by scaling up existing initiative in the production of agricultural advisories and early warnings for cyclones, develop new services for the fisheries and tourism sectors, disseminate accurate weather forecasts and produce or update risk management and adaptation plans, and - Foster collaboration and knowledge exchanging for risk monitoring and management through sustaining and strengthening of SWIOCOF and UIP, The proposed interventions have been developed with the end-users of CP-CS in mind to provide improved CP-CS addressing their needs. Users will be engaged in project interventions to better understand the risks and vulnerability associated to climate-related hazards, and to ensure information is packaged to inform decision at the local level, using the best communication means for each specific group of users. Component 1: Capacity building, institutional development and regional cooperation among NMHS This Component will set up the basis for a regional approach and collaboration for weather and climate monitoring and risk reduction. It will support the adoption of a regional climate services framework (RFCS) that will contribute to developing a common risk culture among IOC member states that reinforces weather data and information sharing in order to better understand and monitor hydro-meteorological hazards in the region (i.e. cyclones, storms with heavy wind and heavy rain). The establishment of a RCC under the aegis of IOC, and for IOC member countries, will provide the following services and facilities to IOC member states: i) regional training and capacity building; ii) calibration and maintenance services for the hydro-meteorological equipment, iii) production of user-tailored, long-range climate products to benefit key climate-sensitive sectors, iv) dissemination of these long-range products within member states via the UIP and SWIOCOF and v) experience and knowledge sharing for adaptation and risk reduction via SWIOCOF and the UIP. The modalities under which the RCC will host and run the regional facilities will be determined in the RCC strategy. Once the RCC strategy, including the roles and responsibilities of each ‘RCC node’, is approved by WMO and relevant member states, multi-lateral agreements between member countries and the IOC will be prepared, following WMO recommendations. The SWIOCOF will be convened by IOC, in coordination with the RCC and NMHS. To support the long-term production of regional services, the multi-lateral agreements will provide details of how each member state will financially contribute to the running costs of the RCC beyond the project’s lifetime – e.g. finance for the maintenance laboratory, training center UIP and SWIOCOF. A regional business model will also be developed to identify additional sources of funding for the RCC from public and private sectors through commercialisation of regional CP-CS (see Annex 3a). Component 1 will also strengthen institutional and financial status of NMHS with particular attention given to retaining skilled staff, which underpins the long-term generation of timely, high-quality climate information products; provide core training to NMHS staff members and ensure the harmonization of climate products across countries, based on international WMO standards. The following Outputs and Activities are planned under Component 1: Output 1.1 A Regional Climate Centre (RCC) and frameworks for CP-CS established Activity 1.1.1 Develop regional and national frameworks for climate services (RFCS & NFCS) Activity 1.1.2 Design the legal, institutional, financial and organisational strategy to establish the RCC Activity 1.1.3 Design the strategy of the regional laboratory for maintenance and annual calibration of equipment, and the strategy of the regional training center (centre/lab will be set up under Output 2.2). Activity 1.1.4 Prepare a strategy to improve Regional Numerical Weather Prediction (RNWP). Output 1.2 Institutional arrangements and operational and financial strategy of NMHS strengthened Activity 1.2.1 Strengthen the institutional, operational and financial strategy of NMHSs for each target country. Activity 1.2.2 Design the transition support plan of each NMHS, DRR institutions and relevant sectoral ministries Output 1.3 Improved staffing of the RCC and NMHSs Activity 1.3.1 Recruit new staff members for the RCC and meteorological services Activity 1.3.2 Train/update training for new/existing staff Output 1.4 Detailed design, technical specification, system integration and tendering process of Project Activities prepared Activity 1.4.1 Conduct baseline study on CP-CS use in each country Activity 1.4.2 Produce a detailed design and system integration for each NMHS Activity 1.4.3 Ensure full system integration from observation stations to delivery of CP-CS to end-user Component 2: High-quality climate-related data, and improved climate risk assessments and climate change projections Under Component 2, equipment for observation and monitoring networks, and information systems will be modernised in the project target countries, based on WMO standards. Moreover, the technical capacities and expertise of NMHS staff members will be improved through training and Research & Development (R&D) activities. To facilitate hydro-meteorological equipment maintenance and organisation of trainings, a regional training laboratory and a regional calibration centre will be set up and/or refurbished and run as part of the RCC. These activities will also enhance regional collaboration, enable cost saving and support the long-term production of effective CP-CS, which require high-quality, well-maintained equipment (e.g. sensors). To further support CP-CS, understanding of climate-related risks on economic sectors and communities will be improved through trainings and the production of hazard and vulnerability maps. Such maps will be developed taking into account climate change impacts on return periods/intensity of selected hazards; moreover, they will be produced using participatory approaches with NMHS, DRR institutions, local authorities of risk-prone areas, public and private sector representing agriculture/fisheries, tourism, water sectors and at-risk communities. The purpose will be to identify main assets at stake and most vulnerable people affected by the selected hazards from a local point of view and based on how people/assets were affected during past events. By indicating the location, frequency, intensity and impacts of hazards, these maps will be useful to develop risk prevention plans to be developed under Component 3. Climate change projections, downscaled sectoral models, and maps, produced under this Component, will be shared with stakeholders in climate-sensitive sectors through the UIP, run as part of the RCC and strengthened under Component 3. The following Outputs and Activities are planned under Component 2: Output 2.1 Enhanced hydro-meteorological observing, monitoring, and impact forecasting services Activity 2.1.1 Modernise/upgrade climate observation and monitoring network. Activity 2.1.2 Modernise/upgrade information system for telecoms, forecasting and climatology. Output 2.2 Regional facilities for maintenance and training established Activity 2.2.1 Establish a maintenance and calibration laboratory Activity 2.2.2 Refurbish regional training center of Mauritius to train observers and forecasters Output 2.3 R&D capacities enhanced to improve understanding of climate and disaster risks on communities and sectors Activity 2.3.1 Organise training to improve downscaling of meteorological data and production of impact-based forecasts Activity 2.3.2 Organise training and R&D activities on climate modelling capacity Activity 2.3.3 Organise training on hydrological modelling for flood prevision (i.e. flood propagation model) Activity 2.3.4 Organise training to produce seasonal agro-meteorological bulletins downscaled at national, regional and local level (if possible). Activity 2.3.5 Develop hazard maps Activity 2.3.6 Develop climate vulnerability maps Component 3: Enhanced use of climate services for climate change adaptation and disaster risk reduction at national and regional levels As regional cooperation for climate risk monitoring is strengthened (under Component 1) and equipment, expertise and understanding of climate risk impacts are enhanced (Component 2), the NMHS will be able to improve the range and quality of their climate-related information, products and services, based on user feedback. The dissemination of CP-CS towards vulnerable socio-economic groups will also be supported, as well as user capacity to use them as decision-making tools. Component 3 particularly aims at equipping decision-makers and communities with adequate tools to prepare for climate-related hazards and to adapt to short- to long-term climate variability and change. It will also strengthen existing communication platforms for the producers and users on CP-CS – such as the UIP and SWIOCOF run as part of the RCC – to ensure a continuous interaction between all stakeholders, collection of user feedback on CP-CS, and a production of CP-CS that evolve based on user needs. A funding strategy to maintain the UIP and SWIOCOF beyond this proposed project will be developed as part of the RCC strategy under Activity 1.1.2. The following Outputs and Activities are planned under Component 3: Output 3.1 Production and dissemination of immediate CP-CS improved at regional and national level Activity 3.1.1 Set up protocols to produce and deliver improved daily weather bulletin, impact-based forecasts, seasonal forecasts and agricultural advisories at national level Activity 3.1.2 Set up protocols to strengthen early warning dissemination for key sectors and among the general public Output 3.2 Short- and long-term risk reduction and adaptation plans improved or developed based on high quality climate data, risk/vulnerability assessments and climate change projections ( Activity 3.2.1 Improve data sharing and coordination with emergency services for on-the-ground interventions at national and local levels. Activity 3.2.2 Update long term climate change adaptation plans responding to the needs of each country be shared on the UIP (Activity 3.3.3). The plans will then be shared on the UIP (Activity 3.3.3). Output 3.3 Training and improved communication with users and end-users of CP-CS established Activity 3.3.1 Train staff members of NMHS and in the RCC on how to package climate-related information in a user-friendly way Activity 3.3.2 Train knowledge brokers – including NGOs, red crescent/cross, local leaders and extension officers – and representatives of sectors in the GFCS areas (public and private organisations) on how to interpret and use CP-CS for decision-making Activity 3.3.3 Strengthen the User Interface Platform (UIP) Activity 3.3.4 Support SWIOCOF to ensure the active participation of climate services users

B.4. Implementation arrangements (max. 1500 words, approximately 3 pages plus diagrams)

The project will be implemented through different entities whose roles and responsibilities are as follow: AFD will be the Accredited Entity (AE), and as such will be responsible for overseeing the project formulation, start-up, implementation, evaluation (including monitoring and evaluation reports, mid-term review and terminal evaluation) and closure. AFD will be in charge of reporting to the Green Climate Fund (GCF). The IOC will be the Executing Entity (EE). The EE will assume overall responsibility for the effective delivery of project inputs and interventions in order to achieve the expected project outputs. To fulfil its role, the EE will set up a Project Management Unit (PMU). The IOC – with the assistance of the PMU - will manage the overall execution of the project. The PMU will be led by a Regional Project Coordinator (RPC). The National meteorological and hydrological services (NMHS) will be the National Executing (NE) entities within each beneficiary country. The NMHS with the support of EE, through the PMU team, will be responsible for project implementation, progress and achieving national objectives. To maintain permanent contact with the beneficiary countries, National Project Coordinators (NPC) will be recruited by the EE and PMU with the involvement of the NE entities. The NPCs will be part of the PMU. Each NE will designate a National Focal Point (NFP), which is a permanent staff member of NMHS to coordinate and liaise with the NPC. Project delivery stakeholder roles, mandates, and governance structure are described and illustrated below : AFD: as the AE for the proposed project, has a strong and established experience working in IOC countries. Its regional headquarter is based in La Réunion island, while three AFD offices are present in Mauritius (covering Mauritius and Seychelles), in Comoros and Madagascar. Moreover, AFD has already four projects/programmes approved by GCF Board (FP021, 42, 95 and 119). As the AE, AFD will manage the funds for the implementation of the project. AFD will have a quality assurance role involving AFD staff in Paris headquarters and at the regional level, within AFD agency in Mauritius (where the IOC has its headquarters) and will involve when deemed relevant its Madagascar and Comoros offices. This quality assurance role will also be ensured through the Regional Project Steering Committee (RPSC) (see below for details) which will contribute to AFD objectives and provide independent project oversight and monitoring functions. Together, AFD and the RPSC will ensure that appropriate project milestones are managed and completed, for example by reviewing progress against set up targets and providing recommendations to set the project back on track if needed. Project quality assurance must be independent of the Project Management function; therefore, the RPSC cannot delegate any of its quality assurance responsibilities to PMU and to the Regional Project Coordinator (RPC). As an Accredited Entity to the GCF, AFD is required to deliver GCF-specific oversight and quality assurance services including oversight of project completion and oversight on project reporting. IOC will be the EE as the regional organisation under which Comoros, Madagascar, Mauritius and Seychelles are members. IOC will execute project activities with the support of the Project Management Unit to be implemented and hosted by IOC headquarters within its sustainable environment and climate change department. An IOC Project Manager (PM) will be assigned by the Secretary General of the IOC at the project start. The IOC already manages several projects with a portfolio of above USD 200 million relating to climate and environment amongst others. The IOC has proven experience in project management with different development partners (including the regional EU-funded ISLANDS and AFD-funded ACCLIMATE multi-year projects); and in coordinating project implementation in its member countries. Currently, two other initiatives involving IOC and dealing with Hydromet and Climate Services are: - EU: the Intra ACP Climate Services Programme: a large programme supported by the EU and the S-ACP involving regional cooperation for the improvement of climate services and related applications; in agreement with the EU. The IOC component of this initiative will be directly integrated in the regional Hydromet Project (funds delegated to AFD); - HYCOS project: a regional project supported by WMO, involving national hydrological and meteorological services and aiming at improving the hydrological observation system. The IOC HYCOS identified project is also a full part of the current project. IOC has also undertaken a process to become a GCF Regional Accredited Entity. As part of this endeavour, IOC has received financial support from the GCF, as well as technical punctual support from AFD’s climate change division, to align its procedures with GCF accredited entity requirements e.g. for auditing and procurement. Additionally, IOC is receiving EU support under the INCA (institutional capacity building) programme, which is aimed at strengthening the institutional capacity of IOC to plan, identify, implement and evaluate projects and programmes to align with the EU 9 pillars. AFD will support IOC in the implementation of the organizational actions already identified within the INCA program. Project Management Unit (PMU): a regional PMU will be established by IOC in its headquarters and will work under the responsibility of the IOC Project Manager (PM). The PMU, which will be constituted of a skilled company or of consortium of skilled companies, will be recruited by IOC based on an international competitive process. The PMU will be headed by a Regional Project Coordinator (RPC). The PMU will support the EE in coordinating the project Accredited Entity, beneficiary countries, and the various partners, as well as in overseeing project activity implementation. The following staff members will form the PMU: - Regional Project Coordinator (RPC): will be a full-time employee of the PMU. The RPC should have strong technical expertise and capacity in the management of large scale, multi-country projects. The RPC will be responsible for the overall project implementation and coordination at regional level. Amongst its mandate the RPC will: i) lead and manage the PMU; ii) liaise with and report to IOC PM iii) liaise and coordinate with NPCs specific interventions in each beneficiary country and/or at the regional level, iv) provide administrative and technical expertise; v) be responsible for the day-to-day implementation and management of the project, and vi) serve as the focal point for interactions between the project stakeholders and partner organisations (e.g. government departments, NGOs, civil society groups) and vii) co-chair the RPSC. Full-time and part-time Officers will provide the administrative, logistical and financial support/expertise to the project and will work under the direct supervision of the RPC. - National Project Coordinators (NPCs): will be hired by the EE and NE with the support of the PMU/RPC. Full-time NPCs will be based in each of the four beneficiary countries and are mandated to support NMHS Focal Points in achieving project goals and objectives. The NPCs will act under the overall guidance and supervision of the RPC. NPCs will be based within National Meteorological Services, namely Comoros Meteorological Services, General Directorate of Meteorology in Madagascar, Mauritius Meteorological Services and Seychelles Meteorological Authority. The NPC should be able to deliver technical expertise. NPCs should act to facilitate daily project execution and follow-up, in close collaboration with NMHS team through a designated Focal Point (FP) or a Project Team to be nominated by each NMHS at the start of the project. NPC mandates will include inter alia i) to liaise with relevant national implementation partners, for example within sectoral ministries and disaster risk reduction institutions, ii) to organise workshops or meetings with regards to project activity, as relevant, iii) and to chair the National Project Steering Committees, organised by the NMHS. Additional PMU staff members based at the IOC office will include: - Hydro-meteorology Expert: A part-time staff member with technical expertise in hydro-meteorology will be recruited to develop ToRs and call for tenders for technical activities, review applications, and to supervise and advise the RPC on the implementation of technical project activities, - Environmental and Social Officer: to ensure appropriate application of environmental and social safeguards during the project, - Financial Officer: to ensure proper accountability and transparency of project expenditures - Procurement Officer: to supervise the procurement process, manage the consultants and equipment acquisition contracts, - Monitoring and Evaluation Officer: to report on technical and financial project implementation and draft evaluation and monitoring reports, - Communication Officer: to develop, disseminate and archive communication material related to the projects, - Administrative Officer: to support project implementation and conduct daily administrative tasks, - In addition to the PMU, a pool of experts with diverse skills will be pre-identified and solicited on an ad hoc basis by the EE to review and assess application and candidate profiles proposed in the offers submitted in response to calls for tenders. The purpose of mobilisation of these experts will be to advise IOC on best candidate/service provider to hire for the project execution. Provisional PMU staff member profiles are presented in Annex 2, FS. Regional project steering committee (RPSC) will be established, coordinated and chaired by IOC. The Committee will include as permanent members: the Regional Project Coordinator (RPC); the National Focal Points (FP), and IOC Permanent Liaison Officers (OPLs) from Comoros, Madagascar, Mauritius, Seychelles and Reunion Island (fifth member of IOC). The RPSC can invite additional participants as observers and advisors among whom: the four National Project Coordinators; the four National Designated Authorities; a representative from AFD; as well as a representative of the EU Commission in Mauritius. A gender balance should be ensured whenever possible. The mandate of the RPSC will involve providing broad strategic oversight, direction and technical advice: i) overseeing project implementation; ii) redefining or readjusting project activities, when necessary; and ii) reviewing/validating annual work-plans and project reports. The RPSC will meet at least once a year – with ad hoc meetings held as and when necessary. It will also be a platform for sharing lessons learnt and good practices among IOC member states. National project steering committee (NPSC) will be convened/organised by the NPC and chaired by the National Focal Points in the NMHS. The NPSC will be responsible for coordination and oversight of activities being delivered by national involved stakeholders. The NPSC will be held twice a year, in order to take stock of progress accomplished during project implementation, identify any issues, and, if need be, raise and address them with the PMU. All stakeholders involved in project implementation during the 6-month reporting period will be invited to attend the meeting and report progress on specific activities they are involved in. The NDA will also attend the NPSC. If deemed necessary, the RPC and the PM could be invited to participate to NPSC at least to once year. The NPSC meeting minutes will be produced by the NPC and shared with the RPC to report lessons learnt, problems and successes at the regional level and to enable adjustments in national implementation as needed. Based on NPSC decisions, the RPC may be asked to carry out additional in-country missions to address specific requirements. While IOC, with support from the PMU, will be responsible for day-to-day execution of the project, overall coordination with other GCF-funded projects and climate change related initiatives will be undertaken by the countries’ National Designated Authorities (NDAs) for the GCF in particular through their implication in the NPSC. For this purpose, it is proposed that the NDAs also sit on the RPSC (see below) in an advisory capacity and to foster country ownership. Figure 2: Project Organisational structure

B.5. Justification for GCF funding request (max. 1000 words, approximately 2 pages)

The Hydromet project as proposed with its components and overall budget of USD 78,060,500, is the most appropriate investment to achieve the desired paradigm shift (see Section D). A USD 59,592,500 grant from GCF is sought by IOC and the Governments of Comoros, Madagascar, Mauritius and Seychelles to invest in climate change adaptation and enable a paradigm shift in the production and dissemination of timely, reliable climate services that respond to user needs among the most vulnerable groups and sectors. These countries are extremely vulnerable to climate-related hazards and change (see FS, section B1), which are projected to increase. Neither the governments nor the vulnerable groups and sectors have the required financial and technical capacity to improve climate services and early warning systems at scale and effectively strengthen risk prevention and mitigation at scale. Comoros and Madagascar, two LDCs, have a large portion of the population living below the poverty line. Their national budget is in significant deficit and, given the socio-economic challenges, their governments prioritise the pressing development needs of their country. Despite being middle- and high-income countries, Mauritius and Seychelles are characterised by high debt levels and wealth inequality; moreover, their economy is highly vulnerable to climate-related shocks. Yet, the benefits of the proposed GCF project will essentially be public goods and the financial returns e.g. for climate-sensitive sectors – will not be sufficient to service debt payments. Historically, most of the revenues of meteorological services come from the public service funding paid by the government. According to WMO, the vast majority of NMSs (over 60% of the world’s NMSs) operate as public entities and received most of their funding (about 80 %) in the form of direct government appropriations. Given existing financial challenges with government budgets in the target SWIO countries, the allocation of significant public funding towards this Project from the four member states is not realistic to achieve the desired paradigm shift, nor can cover all the operation and maintenance costs associated with the required equipment (see Annex 4). Nonetheless, the governments of Comoros, Madagascar, Mauritius and Seychelles are committed to support the proposed project. In Comoros, the government will provide USD 1,267,000 in-kind, and in Madagascar, the government will provide USD 1,018,000 in-kind, which corresponds to the portion of funds these services receive from their respective governments to support current O&M costs. In Mauritius, the government will provide USD 1,742,000 in cash and kind, and in Seychelles the government will provide USD 2,862,000 in cash and kind (refer to Annex 13 for details). These co-financing commitments will serve to finance the construction of new facilities to run and store the equipment to be set up under this project, and towards O&M costs during the project lifetime. Moreover, the AFD and EU have committed to support the proposed project through contributions in grants of respectively USD 5,500,000 and USD 6,105,000. Yet, based on these secured contributions, only a partial improvement of existing meteorological services and capacity building would be possible, and the at-scale benefits in terms of avoided costs and in terms of development of climate services cannot be realised in the absence of GCF investments (see section D.6 and Annex 3a). Funding from other donors has been identified for climate projects (see section B1), but it only covers partially overall regional needs. In addition, activities under the 3 components have been designed to ensure that this Hydromet funding request does not duplicate work supported by other donors and that opportunities for complementarity are identified (see Annex 2 FS). Loan financing is also not envisaged under the proposed project. Indeed, climate data, information, forecasts, warnings and other products, supported under the proposed project are considered to be “public goods” because of their public safety value and cross-cutting socio-economic benefits; hence, it is unlikely that there will be short-term significant financial returns on investment to repay loans. The regional CP-CS developed through the Project will not be profitable in the medium term, so that private sector finance for the Project is not currently realistic. Commercialisation of regional CP-CS will be sought to generate revenues, but it will only partially cover total costs (up to 50% as shown in Annex 3a). By improving service delivery to key national and sub-national stakeholders, additional demand will be created thus facilitating increased budget support in the long term. In addition, successful partnerships will be sought and built up in agriculture/fisheries, tourism, water sectors and other at-risk communities, and are a part of the strategy for ensuring long-term sustainability of the Project’s objectives. Finally, the IOC, representing the beneficiary countries, will be in charge of project implementation and will be the recipient of the funds through AFD financial transfers. By the nature of its status and mandate given by its member states, the IOC is only in capacity to raise funds through grants and cannot go into debt.

B.6. Exit strategy and sustainability (max. 500 words, approximately 1 page)

The hydro-meteorological equipment established through the project will be managed, maintained, upgraded and replaced as needed by the beneficiary governments during and after the project, or at the regional level by IOC/RCC. This will be ensured in the long run by: i) transferring skills to the NMHS to ensure equipment maintenance and renewal; ii) achieving cost-efficiencies through regional complementarities and synergies on risk prediction; iii) demonstrating the value of CP-CS among users and end-users (demand-side) ; and iv) where possible, promoting the commercialisation of these services. This strategic approach will ensure that these stakeholders are able to continue co-producing and using climate services (CP-CS) once the project funding ceases; and can maintain the required O&M of the hydro-meteorological equipment. The strategic approach that underpins long-term development and use of CP-CS in the SWIO region is detailed in Annex 3a and b. - Strengthening of NMHS (including financial strategy) Under Output 1.3, institutional capacity of the NMHS in each country will be strengthened in order to streamline roles and responsibilities, improve their working environment (to retain skill staff) and, in particular, improve their financial efficiency and cash flows. This work will result in a robust institutional strategy for each NMHS, including a cost-recovery and business plan that enables the production and delivery of improved CP-CS. Hence, the NMHS will be capacitated to perform strategic and budget planning and implement effective and efficient management. A long-term business plan for the meteorological services will also be prepared, to consider opportunities for sale of CP-CS in each target countries to generate new income that can be reinvested towards maintenance and update of hydro-meteorological equipment. The NMHS will also be strengthened through training and capacity building interventions for their staff members including on the maintenance of hydro-meteorological equipment, and through involvement in R&D activities under Output 2.3. Together with the institutional strengthening interventions, this will contribute to bring the NMHS of the four target countries closer to WMO Category 3 ‘Full climate services’. A regional approach favouring cost-effectiveness, partnerships and integration within regional hydro-meteorological initiatives Cost-effectiveness will be achieved through improved collaboration for risk monitoring in Comoros, Madagascar, Mauritius and Seychelles, under the leadership of IOC. Collaboration will be secured through the establishment of a RCC under which IOC and the four national meteorological services will become members. Under the RCC, a regional maintenance laboratory and a training centre will be established. The maintenance laboratory, in particular, will carry out maintenance work and calibration on existing and newly acquired hydro-meteorological equipment. This reduces current extra costs of sending sensors and other equipment with a limited lifetime and in need of regular maintenance overseas for maintenance (currently Kenya and South Africa). Staff members of the NMHSs will also be trained at the regional training center currently established in Mauritius, which will be refurbished with relevant equipment and software that can be shared across the region. The RCC, set up under the proposed project, will be established to become part of WMO RCC-network. Coordination among the member states will be ensured by IOC, which plays a key role in the SWIO region. Indeed, IOC is the only regional institution of the South West Indian Ocean states. Funded by its member states in 1984 it has been financially supported by these states since then. Finally, the project will ensure the participation of the four beneficiary countries to WMO WHYCOS initiative, by implementing the recommendations identified in HYCOS study for the Indian Ocean Region (see Annex 22 HYCOS study). Building demand and understanding of CP-CS that are continuously improved based on user feedback The project is designed with end users in mind, thereby placing significant resources on addressing end-user needs. The CP-CS produced under this project will be co-developed with users during workshops, consultations and joined training events with the NMHS, DRR institutions, sectoral users and communities. Users will have a greater understanding of CP-CS. In addition, user feedback on CP-CS will be systematically collected via the UIP (the online platform will include a user page for users to assess the quality and usefulness of the CP-CS in their sectors) and during SWIOCOF, as users of CP-CS will be invited to share their experience and recommendations for CP-CS improvements. This will ensure the hydro-meteorological services continue to evolve as user demands change, which will contribute to long-term sustainability through keeping the relevance of hydro-meteorological services and raising demands. In the context of climate change, the demand for improved CP-CS will increase, thereby adding value to the production of such services over the long-term. Most of the CP-CS generated by the proposed project will be based on open-source formats and accessibility will be ensured through the UIP. This will build a community of practice, at the regional level, for using and improving CP-CS, coordinated under the RCC and by IOC, through the organisation of SWIOCOF. Strategy for CP-CS commercialisation As CP-CS improve, demand from the private sector for such services is expected to increase. Preliminary discussions in the 4 countries with tourism and agribusiness representatives indicate a potential interest in paying for reliable, timely CP-CS. Annex 3a provides an overview of expected returns on investments through the sale of CP-CS during and beyond the project lifetime. This interest will be further investigated under the proposed project: detailed business plan will be developed for each NMHS to help them sell their products, designed to respond to the specific demands of users in the private sector (including insurance sector). The potential income stream from private sector is estimated to contribute up to 50% of NMHS budgets; this income will be redirected towards equipment maintenance, upgrade or renewal, running costs of the RCC and its various components (including a training center and the UIP), and towards the continuous production of high-quality CP-CS. Finally, it should be noted that a draft operation and maintenance budget has been prepared for the proposed project. This budget estimates that during the five years of the implementation of the project, the O&M budget following the equipment installation is about USD 6 million and will partly be covered by the governments of Comoros and Madagascar (in-kind) while the governments of Mauritius and Seychelles will take full care of their respective O&M budgets. The O&M budget will be updated during project implementation, based on a more detailed examination of current human and financial resources, and fine-tuned estimates of operation and maintenance needs for each country. The governments of the four beneficiary countries will furthermore establish an expenditure monitoring system for hydro-meteorological services to allow an effective tracking of the resources allocated and spend on operation and maintenance. After the project ends, the four beneficiary NMHS together will be able to fully cover their O&M costs, as their staff will have been trained under this project, and a regional maintenance laboratory established.

| # FINANCING INFORMATION |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| C.1. Total financing |  |  |  |  |  |  |  |  |  |  |
| (a) Requested GCF funding (i + ii + iii + iv + v + vi + vii) |  | Total amount |  |  |  |  | Currency |  |  |  |
|  |  | 59 592 500 |  |  |  |  | million USD ($) |  |  |  |
| GCF financial instrument |  | Amount |  | Tenor |  |  | Grace period |  | Pricing |  |
| (i) | Senior loans | Enter amount |  | Enter years |  |  | Enter years |  | Enter % |  |
| (ii) | Subordinated loans | Enter amount |  | Enter years |  |  | Enter years |  | Enter % |  |
| (iii) | Equity | Enter amount |  |  |  |  |  |  | Enter % equity return |  |
| (iv) | Guarantees | Enter amount |  | Enter years |  |  |  |  |  |  |
| (v) | Reimbursable grants | Enter amount |  |  |  |  |  |  |  |  |
| (vi) | Grants | 59 592 500 |  |  |  |  |  |  |  |  |
| (vii) | Result-based payments | Enter amount |  |  |  |  |  |  |  |  |
| (b) Co-financing information |  | Total amount |  |  |  |  | Currency |  |  |  |
|  |  | 18 468 000 |  |  |  |  | million USD ($) |  |  |  |
| Name of institution |  | Financial instrument | Amount |  | Currency |  | Tenor & grace | Pricing |  | Seniority |
| AFD |  | Grant | 5.6 |  | million USD ($) |  | Enter years Enter years | Enter% |  | Options |
| U.E. |  | Grant | 6 |  | million USD ($) |  | Enter years Enter years | Enter% |  | Options |
| Gov of Comoros |  | In kind | 1.267 |  | million USD ($) |  | Enter years Enter years | Enter% |  | Options |
| Gov of Madagascar |  | In kind | 1.018 |  | million USD ($) |  | Enter years Enter years | Enter% |  | Options |
| Gov of Mauritius |  | Grant | 1.742 |  | million USD ($) |  | Enter years Enter years | Enter% |  | Options |
| Gov of Seychelles |  | Grant | 2.862 |  | million USD ($) |  | Enter years Enter years | Enter% |  | Options |
| - Total financing (c) = (a)+(b) |  | Amount |  |  |  |  | Currency |  |  |  |
|  |  | 78.060 500 |  |  |  |  | million USD ($) |  |  |  |
| (d) Other financing arrangements and contributions (max. 250 words, approximately 0.5 page) |  |  |  |  |  |  |  |  |  |  |
| C.2. Financing by component |  |  |  |  |  |  |  |  |  |  |
| Component; Output; Indicative cost million USD ($)million USD ($); GCF financing; Co-financing. Amount million USD ($)million USD ($); Financial Instrument; Amount million USD ($)million USD ($); Financial Instrument; Name of Institutions. Capacity building, institutional development and regional cooperation; A Regional Climate Centre and frameworks for Climate Services (CP-CS) established in the SWIO region; 850 000; 782 000; Grants; 68 000; Grants; AFD. Institutional arrangements and operational strategy of national met. services strengthened; 1 200 000; 1 102 000; Grants; 98 000; Grants; AFD. Click here to enter text.; Improved staffing of the RCC and national met. services; 5 240 000; 4 814 000; Grants; 426 000; Grants; AFD. Detailed Design, technical specification, system integration and tendering process of Project Activities; 2 296 000; 2 109 000; Grants; 187 000; Grants; AFD. Sub-total Component 1; 8 807 000; 779 000. Improved monitoring, risk analyses and forecasting; Enhanced hydro-meteorological observing, monitoring, and impact forecasting services; 31 653 500; 28 225 500; Grants; 3 428 000; Grants; AFD; EU; gov.. Click here to enter text.; Regional facilities for maintenance and training established; 1 500 000; 1 378 000; Grants; 122 000; Grants; AFD. Click here to enter text.; R&D capacities enhanced to improve understanding of climate and disaster risks on communities and sectors; 7 570 000; 6953 000; Grants; 617 000; Grants; AFD. Sub-total Component 2; 36 556 500; 4 167 000. Strengthened climate services delivery and early warning systems at national and regional level; Production and dissemination of immediate CP-CS improved at regional and national level; 8 970 000; 4 296 000; Grants; 4 674 000; Grants; AFD; EU. Click here to enter text.; Short- and long-term risk reduction and adaptation plans improved or developed based on high quality climate data, risk/vulnerability assessments and climate change projections (produced under Outcome 2); 800 000; 384 000; Grants; 416 000; Grants; AFD; UE. Click here to enter text.; Training and improved communication with users and end-users of CP-CS established; 6 350 000; 4 578 000; Grants; 1 772 000; Grants; AFD; UE. Sub-total Components 3; 9 258 000; 6 862 000. Sub-total all Components; 66 429 500. Project management; PMU; 3 637 000; 3 037 000; Grants; 600 000; Grants; AFD. O&M; 7 994 000; 1 934 000; Grants; 6 060 000; Grants; AFD; Gov.. Indicative total cost (USD); 78 060 500; 59 592 500; 18 468 000. |
| C.3 Capacity building and technology development/transfer (max. 250 words, approximately 0.5 page) |  |  |  |  |  |  |  |  |  |  |
| C.3.1 Does GCF funding finance capacity building activities? |  |  |  |  |  | Yes ☒ No ☐ |  |  |  |  |
| C.3.2. Does GCF funding finance technology development/transfer? |  |  |  |  |  | Yes ☒ No ☐ |  |  |  |  |
| Overall, the GCF will be investing USD 11,583,000 to support capacity building interventions. These include: - core training on climate services, climate related risks and impacts on communities and sectors for 15 staff members of NMHS, DRR institutions and in climate-sensitive sectors (USD 4,630,000); - trainings to improve the capacity of staff members in NMHS to produce locally relevant forecasts (USD 459,000), - training and R&D activities to downscale climate change projections (USD 643,000), - training on hydrological modelling for flood prevision (USD 459,000) and - trainings to develop agricultural seasonal products (USD 459,000). - In addition, hazard maps and vulnerability maps will be produced (USD 4,933,000). These capacity building interventions, implemented under Component 1 and 2 of the project, will be critical to ensure the production of CP-CS that are timely, accurate and target the needs of users in climate-sensitive sectors. The core trainings under Component 1 (Activity 1.3.2) will enhance understanding of how climate-related hazards and change can affect key sectors and communities and how CP-CS can help reduce these negative impacts; while the technical trainings to be implemented under Component 2 (Activities 2.3.1-2.3.4) will improve the capacity of NMHS staff members to produce accurate, locally-relevant short- to long-term forecasts that can serve as decision-making tools to reduce climate-related vulnerabilities. Finally, Activities 2.3.5 and 2.3.6 will serve to build understanding in the beneficiary countries of areas most impacted by climate-related hazards, and the vulnerability of the population to these hazards. It should also be noted that the regional aspects of the project that underpin collaboration and knowledge sharing provide an opportunity for countries to leverage each other’s strengths and capitalise on successful national initiatives; the regional facilities to be set up under the RCC, and shared responsibilities for equipment maintenance and calibration, training and R&D, or UIP management will also increase the capacity and expertise of each country in a specific field (depending on the regional component they will host). |  |  |  |  |  |  |  |  |  |  |

# EXPECTED PERFORMANCE AGAINST INVESTMENT CRITERIA

This section refers to the performance of the project/programme against the investment criteria as set out in the GCF’s Initial Investment Framework.

D.1. Impact potential (max. 500 words, approximately 1 page)

The project envisions to increase climate change resilience and reduce loss of life, property, and livelihoods due to climate-induced threats in Comoros, Madagascar, Mauritius and Seychelles. The potential of the project to contribute to the achievement of the GCF’s objectives and result areas is described in Section H1. The project will contribute to the GCF Adaptation Impact: Increased sustainable, climate resilient development, in the following ways: 1. Strengthened institutional and regulatory systems Institutional, financial and operational systems of NMHS will be strengthened through Component 1; moreover, regional cooperation for climate risk monitoring and management will be institutionalised in the long-term by establishing a RCC with operational nodes in each member country. Regulatory frameworks to produce and disseminate CP-CS will be developed (Activity 1.1.1) focusing on the end-users of these services. Capacity building for governmental stakeholders in sectoral ministries and in the NMHS will also be provided to enhance understanding of risk prediction and exposure, thereby improving preparedness and response planning capacity (Activity 1.3.2). 2. Increase generation and use of CP-CS in decision-making The project will support the generation and use of specific CP-CS in three sectors, namely agriculture, fisheries and tourism. Tailored CP-CS will be developed in partnership with users in these sectors responding to user needs, whilst ensuring use of best communication means to maximise user outreach. The number of users of CP-CS will be assessed during the baseline assessment for each country, under Activity 1.4.1. Progress in terms of number of users of CP-CS will be re-assessed through project mid-term and final evaluations. Based on increased use of CP-CS in agriculture, fisheries and tourism, the average annual benefits of an EWS in terms of avoided costs were estimated to be about $14 million for the IOC region as a whole (see Annex 3a). Other products, developed under the proposed Components 2 & 3, including downscaled climate change projections, climate hazards and vulnerability maps, weather bulletins and EWS, will inform decision-making in the short- and mid-term. The CP-CS produced under this project will also be shared on the UIP to further leverage these new resources, and their use beyond targeted sectors. Beyond the project timeline, sector-specific services could be up-scaled and replicated in other priority sectors building on the methodologies, capacity building, technical support and lessons learned from the proposed project. 3. Strengthened adaptive capacity and reduced risk exposure The project will focus on end-users of the CP-CS to ensure production and dissemination of services is relevant and efficiently reach targeted users. Most relevant communication platforms – cellphone, radio or Internet – will be identified for each target users and CP-CS will be “packaged” based on their requirements. For example, agricultural advisories will be disseminated by cellphone and radio in Comoros, Madagascar, and Mauritius (Activity 3.1.1). It is expected that farmers benefiting from the services will achieve a net profit of +10 to +15 % and a 2 to 5 % reduction in the cost of cultivation. Likewise, with access to reliable climate information, fishermen will be able to make informed decisions about when to set sail, and to protect their equipment, assets and catch from climate extremes (Activity 3.1.2). The expected result is a -30% reduction in risk exposure at the end of the project (see Annex 3a). 4. Strengthened awareness of climate threats and risk-reduction processes This will be ensured as CP-CS are designed with the end-users, who will be trained in their meaning and use. Moreover, knowledge-brokers and key community members will be trained on risk preparedness and mitigation measures (Activity 3.3.2), and all services shared on knowledge platforms such as the UIP. Awareness raising campaigns will also be supported by the project under Activities 2.3.6 and 3.2.1. The benefits of the proposed project will span across the following areas: i) receiving direct agricultural advisories on cropping calendar and best varieties, droughts, heavy rainfalls and other extremes; ii) receiving ‘safety at sea’ alerts and warnings on algal blooms episodes; iii) receiving early warnings for cyclones; iv) accessing more accurate, locally-relevant weather bulletins; and v) receiving adequate preparedness advice and emergency support before, during and after climate-related hazards. All together, these benefits will enable climate change adaptation, risk prevention and protection of assets and livelihoods in the four target countries. The expected total number of beneficiaries benefitting from reduced vulnerability to climate change is estimated to be 19,453,286 (66.5%) from a total population of 29,241,477 across the four islands; of which at least 50% will be women beneficiaries. Direct project beneficiaries were estimated at 21% of the total population (6,054,909); and additional i ndirect beneficiaries at 46% (13,398,377). The approach used to estimate number of beneficiaries – in particular the additional indirect beneficiaries – is based on the delivery of CP-CS in targeted sectors; and based on access to improved forecasts and more timely early warnings via cellphone, radio and the Internet. See Section 5.4, Annex 2 for additional details on beneficiary calculations. Total population: 845,477 in Comoros; 27,000,000 in Madagascar; 1,300,000 in Mauritius; and 96,000 in Seychelles - Indirect beneficiaries: Proportion of the population with access to radio, cellphone and/or Internet access (whichever is the highest): 60% in Comoros (cellphone subscription) or 507,286 people; 65% in Madagascar (radio) or 17,550,000 ;100% in Mauritius and Seychelles (cellphone). Of which 50% are women. Proportion of the population working in the tourism sector in Mauritius and Seychelles, being less affected by economic losses if climate-related risks are better anticipated, have likely access to cellphone or the Internet; therefore, they are included in the previous calculation. Direct beneficiaries are also excluded from indirect beneficiary calculation. Estimated indirect beneficiaries = 13,398,377, which is 46% of the total population over the 4 islands; of which 50% are women. - Direct beneficiaries: Proportion of the population working in agriculture and fisheries with access to communication channels: Comoros: 481,922 (57% of pop.) people working in agriculture and fisheries, out of which 60% have access to communication means = 289,153 Madagascar: 18,900,000 (30% of the 70% of pop.) working in agriculture and fisheries, out of which 65% have access to communication means = 5,670,000 Mauritius: 92,300 (7.1%) working in agriculture and fisheries, and with access to communication means. Seychelles: 3,456 (3.6%) working in agriculture and fisheries, and with access to communication means. Total expected direct beneficiaries = 6,054,909 which is 21% of the total population over the 4 islands; of which 50% women. The proposed approach for beneficiary calculation remains conservative for the following reasons: i) climate hazard alerts and preparedness and prevention advices can be spread by word of mouth, signs displayed in communities, sirens e.g. from the mosque, and trained knowledge brokers regardless of radio/cellphone ownership, therefore indirect beneficiaries of the proposed project could be close to 100% of the population; ii) not only will direct employees in the tourism sector benefit from CP-CS but also restaurants (therefore farmers and fishermen), shop and hotel owners, informal workers, investors, etc.; iii) most sectors will benefit indirectly from improved CP-CS; and iv) the population of the four countries will benefit from improved production in agriculture and fisheries sector.

D.2. Paradigm shift potential (max. 500 words, approximately 1 page)

The project will effect a paradigm shift that results in enhanced climate-resilience in Comoros, Madagascar, Mauritius and Seychelles. It will catalyse impacts beyond the project’s lifetime and economic sectors for which specific CP-CS will be developed. This will be achieved through an innovative, integrated approach that not only enhances the technical and technological capacities to monitor and forecast climate-related hazards and extremes – as is often the case in similar projects –, but also strengthens institutional settings and frameworks supporting climate risks reduction and adaptation at regional and national scale. As such, the proposed interventions address structural needs in each of the target countries and take on a “systems-based” approach (i.e. incorporating strategic, institutional, financial, human resources aspects as opposed to only addressing technical/equipment improvements). As it is crucial to tackle climate related events at a large spatial scale (e.g. cyclones), the regional aspect of the project is a strength that will further enhance project outcomes. Regional collaboration will be facilitated by IOC, the sole regional institution in the SWIO region. Created by its member states 36 years ago, IOC has an established experience to implement large-scale climate-related projects and programmes in the region; moreover, IOC has a key role bringing together the island countries of the SWIO region, coordinating the implementation of project’s activities in these countries, and protecting their interests. The project meets the following GCF requirements: Potential for scaling up and replication: All interventions are designed based on existing best practices and recommendations from the WMO and are building on, complementing and upscaling other past and ongoing climate services-related projects in the four target countries (see Section B.1). The regional collaboration for risk prevention, fostered by IOC, will be institutionalised through the establishment of a RCC. The RCC for the SWIO region will replicate success stories like the Caribbean Institute for Meteorology and Hydrology (CIMH) which was officially designated as the World Meteorological Organization (WMO) Regional Climate Centre (RCC) for the Caribbean region in 2017 after a four-year process. Technical improvements for enhanced risk monitoring and forecasts will also be supported at regional level by setting up a Numerical Weather Prediction (NWP) regional team, building up on the BRIO project. The project scalability will be further enhanced by sharing lessons learned and best practices through the UIP and during SWIOCOF, which will both be strengthened by the project (Activities 3.3.3 and 3.3.4); the UIP, as well as the NCOF and SWIOCOF will also be used to share the climate projections, weather forecast and CP-CS developed under this project, in order to facilitate their use by other – non-direct beneficiary – sectors and socio-economic groups. It is expected that CP-CS use will reach all sectors during and after the implementation of the project, given the enhanced production of high-quality products and services. Users may include stakeholders from the private sector, which would be willing to pay for good-quality CP-CS that can inform key decisions (e.g. stakeholders from the tourism industry in Madagascar have already confirmed future possibility of buying adequate CP-CS relevant to their activity). The potential contribution of the private sector to CP-CS has been estimated at up to 50% from the commercial sector (see Annex 3a). Additional financial returns for the meteorological services will enable further upscaling their observation networks and expanding the delivery of CP-CS to new areas and users across the country. Potential for knowledge sharing and learning: The RCC training center design and session events for SWIOCOF as well as UIP will be strengthened to facilitate exchange of climate-related information and risk management experience across the four countries. It will also promote collaboration for the prediction of climate-related risks such as cyclones. Particular attention will be on promoting information sharing with the end-users of the climate services, i.e. the vulnerable communities. Hence, best communication means for vulnerable remote communities will be identified – including language, cultural and gender issues, communication channels, etc. Moreover, knowledge broker institutions for risk prevention will be trained to enhance risk understanding at the local level, and directly provide relevant advice and support for risk preparedness and recovery to local communities (Activity 3.3.2). Contribution to the creation of an enabling environment: Climate-related information is not disseminated on a regular basis to climate sensitive sectors in Madagascar and Comoros. In Mauritius and Seychelles, information is disseminated but is not always timely or accurate, especially for fast-onset events such as flash floods. It is also noted that information released by the NMHS is very technical and cannot always be used for decision-making. By modernising the NMHS, strengthening institutional settings (Output 1.2), and improving collaboration and communication between producers and end-users (Activity 1.1.1), the project will improve the quality and usability of climate products. Moreover, training will be provided to producers of CP-CS on how to produce user-tailored CP-CS (Activity 3.3.1) and to users and end-users of climate services to enhance their understanding and use of climate products (Activity 3.3.2). This process will be supported through climate outlook forums (COF) which are being hosted on a regular basis at national and regional levels, as well as through dedicated training sessions implemented during the project lifetime. Finally, the project will set the basis to foster private sector investments into climate services by strengthening the capacities of NMHS to develop and deliver climate products that respond to user needs, e.g. the tourism industry. Contribution to the regulatory frameworks and policies: The proposed project will strengthen the institutional set up of the NMHS in the four target countries and update existing climate change adaptation plans. Moreover, a regional climate services framework will be developed and serve as umbrella under which national climate services strategies will be prepared. The climate-related data produced under project Output 2.3 and shared on the UIP can also inform decision makers to develop policies and strategies in climate-sensitive sectors. This will support a risk reduction culture in Comoros, Madagascar, Mauritius and Seychelles, as well as the harmonization of equipment and processes.

D.3. Sustainable development (max. 500 words, approximately 1 page)

The project fully supports the implementation of SDGs in the four countries, in particular SDG 2: End hunger, achieve food security and improved nutrition; SDG 3: Ensure healthy lives and promote well-being; and SDG 13: Take urgent action to combat climate change and its impacts. In addition, the project supports the operationalisation of the Sendai Framework[4] targets for Disaster Risk Reduction (SF-DRR) as well as risk-informed sustainable development. 1. Environmental co-benefits The project will reduce the vulnerability of exposed populations and assets to climate change. As people are less affected by climate-related hazards, and their economic activities become more resilient, pressure on the natural environment will decrease. For example, agricultural advisories and weather alerts will enable climate-smart decision making among farmers and fishermen. Farmers will be able to use adequate crop varieties based on advisories, while farmers and fishermen will be able to protect their equipment and harvests as they receive risk alerts. As a result, they will suffer less losses and damages from climate variability, change and extreme. This will, in turn, reduce pressures on the environment as, in many LDC such as Madagascar or Comoros, unsustainable extraction of wood for charcoal production is a practice used to compensate for climate-related agricultural losses. In addition, the design and management of small dams for irrigation, for example, will also benefit from better climate data and dissemination services; if dams are better designed to capture water most efficiently, pressure on the ecosystems for water extraction will be reduced. 2. Social co-benefits including health impacts The project will contribute to improve well-being, health and save lives. This will be achieved through strengthening EWS and other climate services such as the production and dissemination of agrometeorological information to improve agricultural productivity supporting food security, and algal blooms warnings to avoid contamination risks in the fisheries sector. The proposed Hydromet project will provide information with regards to floods and flash floods risks, as well as improve the production and dissemination of early warnings towards vulnerable communities and raise awareness of risk prevention and mitigation measures. With better information at hand and access to timely warnings, communities can take proactive steps to protect their lives and assets against potential climate-related disasters. Likewise, fishermen and farmers will be able to move their assets including fishing/farming equipment to protect them against climate extremes such as cyclones and storm surges. Finally, the project will update climate change adaptation plans, which will in turn improve the quality of life in the four target countries in the long-term. 3. Economic co-benefits Significant economic gains can be expected from the project, both in terms of reduced losses linked to climate-related hazards and increased financial returns/productivity in key economic sectors like agriculture and tourism. The Annual Average Benefits linked to EWS in terms of costs avoided has been assessed to be around USD 14 million for the entire IOC region. The Annual Average Benefit from agro-climatic services have been estimated at USD 29,93 million per year for the period 2026-2030 to up to 89,8 million per year for the period 2041 to 2070 for the 4 countries. Finally, the net present value (NPV) of the project is estimated at USD 956 million at 5% discounting rate. Sensitivity analysis shows that NPV is still positive (USD 643 million) even if the project benefits are 30% lower than expected. Moreover, in the long term, commercial revenues in the NHMS can be expected through the sale of CP-CS, and will progressively replace part of public funding of NMHS, covering from 30% to almost 50% of their budget. For additional details on the economic and financial benefits of the project, please read Annex 3a, Economic Analysis. 4. Gender-sensitive development impacts The project includes a Gender Assessment and Action Plan (see Annex 8), which will operationalise gender-responsive adaptation action through the project results framework. Hence, the gender mainstreaming approach of IOC Hydromet will include: mainstreaming gender-responsive approaches for the design of CP-CS products, hydro-meteorological systems, and EWS; promoting gender balance through the technical and maintenance capacity-building activities as well as institutional development targeted for hydro-meteorological networks, equipment and systems; establishing gender-aware policy frameworks to inform collaboration between key sectors and national/regional hydro-meteorological services; and pioneering gender mainstreaming analyses and praxis regarding hydro-meteorological systems, EWS and CP-CS in the Indian Ocean region and islands.

D.4. Needs of recipient (max. 500 words, approximately 1 page)

The SWIO region has been recognised as a ‘climate hotspot’ (see Annex 2, section B1). The affected population and physical damages resulting from climate-related hazards are likely to rise in the coming years, in the context of climate change. Despite different socio-economic contexts – with Comoros and Madagascar classified as LDCs, Mauritius as upper-middle income country and Seychelles as high-income country – the economy and populations of these four islands are extremely vulnerable to climate-related hazards. In Comoros and Madagascar, the population is highly reliant on agriculture and fisheries, two key economic sectors which are severely affected by increased air and sea temperature, tropical cyclones, sea level rise and coastal erosion. In Mauritius and Seychelles, the economy is highly depending on tourism, which is also threatened by tropical cyclones, increased occurrence of floods, flash floods and landslides, and storm surges resulting in coastal erosion. These four islands are also characterised by microclimates, which makes it all the more difficult to predict climate-related hazards and therefore implement risk mitigation or avoidance measures. More precisely, there is a lack of locally-relevant climate and weather information to inform decision-making processes, a limited production and dissemination of climate services that can help reduce risk exposure and vulnerability among communities and sectors and limited cooperation at the regional level to monitor risk and share risk-related information in the SWIO countries. This is because of the limited technical capacity within NMHS, as well as relevant expertise, training programmes and R&D activities to respond to users’ needs in terms of CP-CS (see Annex 2). Improving CP-CS to respond to user needs, reduce vulnerability to climate hazards and change, and ensure sustained economic growth also requires significant investments, which cannot be met by the NMHS of the four target countries: while Comoros and Madagascar are considered low-income countries, all four countries are characterized by their high level of debt; their economy is threatened by climate change, with significant public spending already noted to recover from the physical damages resulting from climate-related hazards and emergency responses (see Annex 3a). Existing initiatives and investments in the four target countries supporting the improvement of CP-CS – as described in section B.1– have been assessed, and are complementary to the project; however, these interventions are limited to specific areas of a country and/or to a specific sector and cannot achieve the desired paradigm shift. Timely, reliable weather, climate and hydrological monitoring and forecasting are necessary to equip decision-makers with the adequate information for short-term risk reduction and EWS set up to long-term adaptation planning. To achieve this in Comoros, Madagascar, Mauritius and Seychelles, significant investments will be required not only to equip or upgrade observation networks and foster the production of climate services that respond to user needs in individual countries; but also to support the harmonisation of processes and enhanced communication and knowledge sharing at the regional level, through the establishment of a RCC and framework for climate services. These latter interventions (i.e. with a regional scope) which underpin improvements at the national level, are new in the region. The outcomes of the proposed project will enable decision-making that will enhance livelihoods of the most vulnerable communities and support economic growth in key climate-sensitive sectors; increased economic growth will, in turn, support the production of climate services beyond the project’s lifetime.

D.5. Country ownership (max. 500 words, approximately 1 page)

It should also be noted that the project responds to a call to provide support at scale to NMHS to the Indian Ocean region launched in 2010 by the African Union (AU) and the WMO. The project concept was developed by the IOC, which received repeated requests and approval from its ministerial council to develop Hydromet as a full-scale funding proposal for the GCF. The Funding Proposal was prepared based on extensive in-country consultations and field visits which took place between May and November 2019, including one-on-one meetings with decision-makers in the public and private sector, focus group interviews organised with vulnerable communities (especially women), and a series of workshops with relevant government and sector representatives to gather feedbacks on initial project interventions (see Annex 7). The four country NDAs have also been consulted during the project development phase. Moreover, the NDAs will follow the progress of the proposed project implementation in their country, through regular presence at National Project Steering Committees and Regional Project Steering Committee (see section B.4), in particular to ensure project alignment with their respective country’s climate change adaptation objectives, and its complementarity and synergies with other existing initiatives in this field. The project is aligned with several international and national policies and strategies pertaining to climate change adaptation and disaster risk reduction (details on existing policies and strategies can be found in Annex 2). In a nutshell, these include: Comoros: the country has submitted its NAPA in 2006, which emphasises the need to “establishing and further developing early warning systems’, is currently developing its NAP and has submitted its NDC in 2016, which underlines the importance to develop an effective cross-sectoral early warning system. Comoros’ Strategic Plan 2017-2020 also notes in particular the current lack of stations, difficulties delivering services on time, and lack of capacity in the department. Madagascar: the NAPA, submitted in 2006, highlights that improvements in climate services and development of agro-climatic products are critical to climate change adaptation; the NAP process was launched in 2011, and the NDC submitted in 2015. In this document, climate services, EWS, and sector-specific climate risk management plans for agriculture and water are listed as short-term priorities. Madagascar has a National Climate Change Management Policy (PNLCC, 2012), and a National Strategy for Disaster Risks Management (NSDRM, 2016-2020), which all underline the need to strengthen climate services. Mauritius: the country has started its NAP process and submitted its NDC in 2015; both plans support climate change adaptation and promote use of EWS to enhance climate resilience. Moreover, the country has a National Climate Change Adaptation Policy, which notes the importance of information gathering and regional and international collaboration to implement adaptation goals. Seychelles: the country has submitted its NDC in 2015, which highlights climate change impacts on fisheries, infrastructure, and tourism, among other sectors; the necessity for research and resources to “predict, prevent and respond to disasters” is emphasised. The Seychelles National Climate Change Strategy (2009) needs to be updated to support the implementation of the country’s new Climate Change Policy (currently under development). Finally, the project will support the implementation of SDGs in the four countries, in particular target 13: ‘Take urgent action to fight climate change and its impacts’. Hydro-meteorological and early warning services, as those to be strengthened under the proposed project, are key enablers for broad range of adaptation decisions.

D.6. Efficiency and effectiveness (max. 500 words, approximately 1 page)

The Hydromet project, with its inter-linked components, is the most appropriate investment to achieve climate change adaptation objectives. In the absence of GCF funding – based on financial support from AFD and the EU only, respectively USD 5,790,00 and USD 6,000,000– it would be possible to improve meteorological services and capacity building partially but prioritizing a small sub-set of equipment in each country and focusing on pilot projects only in the most vulnerable areas instead of servicing CP-CS to key sectors nationally. Furthermore, the project would not be able to address the enabling environment and frameworks as set under Component 1. The full benefits in terms of avoided costs, long lasting gains in terms of development of climate services, for and by the private sector - which are detailed in Annex 3a Economic Analysis – would not be realized in the absence of GCF investments. Without the support of the GCF, the Hydromet project will lose the major part of its components, namely all the infrastructure allowing strengthened climate services delivery and early warning systems at national and regional level. In this scenario, the major benefits from the original Hydromet project, i.e. upgrading, refining the warnings from general cautionary advice to a detailed, location-specific, model-based forecasts of hazard evolution, expected impacts or consequences and precautions for particular vulnerable segments of society will no longer be possible. All benefits of the annual average losses evaluated to approximatively USD 14 million for the four countries will not be achieved. The benefits for the private sector will also be affected. The process of developing user-tailored climate services typically involving the translation of temporal and spatial information about the climate into decision-support tools to suit the needs of specific sector applications, will no longer be possible. With GCF support, the improved agricultural profits attributable to Hydromet for the four countries have been evaluated to be around USD 29,93 million per year for the period 2026-2030 to up to 89,8 million per year for the period 2041 to 2070, with a conservative assumption of a 10% increase in yields for 10% of the agriculture sector using agroclimatic services. Without GCF funding, the absence of major infrastructure will seriously reduce the ability of NMHS to produce tailored seasonal weather and climate forecasts and warnings at the appropriate timescale and geographic scale. We reviewed the assumptions of a 1% productivity increase for 2% of the agriculture sector under a no-GCF scenario. Total incremental value of agriculture production (USD million) during 2026-2030; Madagascar; Comoros; Seychelles; Mauritius. With the GCF Funds; 21.8; 0.4; 0.03; 7.7. Without the GCF funds; 0.87; 0.02; 0.00; 0.31. Impact on the economic rate of return The NPV of the project, with the GCF funds, have been assessed to USD 956 million for an 5% discounting rate. Without the GCF funds, the NPV of the project becomes negative at - USD 0,4 million. The major share of benefits, evaluated at a total of USD 956 million at 5% discounting rate, will be lost. The main barrier to the development of the Hydromet project without GCF support is a lack of funding. The target countries are not in a position to finance the Hydromet project alone as indicated in section B.5, without the contributions of the AFD, the EU and the GCF. The overall investment weight of the Hydromet project (±USD 78 million) represents 0.27 % of the combined GDP of the four countries (USD 28,343 million). In addition, the per capita burden on the four countries (29,147,444) to implement Hydromet alone would be approximately USD 2.6 per capita. This level of investment is much higher than the spending ratios of other states in the world. Most NMHS are funded in the range of 0.010-0.050 % of gross domestic product, with a total average of 0.012 %. Per capita spending on NMS in US $ 0.10 for at least one NMHS in every World Meteorological Organization (WMO) region-to almost US $ 13.00. The average for developing countries is about US $ 3.50 per capita of national population, and the average for the least developed countries is about US $ 0.25. The financing structure of the project is essentially based on investment subsidy for the implementation of the project, and co-financing (from Mauritius and Seychelles) for construction work and the operating and maintenance costs. As a result, the financial model will not weigh on the public debt of the targeted countries. Country ownership of operating and maintenance expenses will also have no impact on the public debt, since it will be achieved by strengthening the capacity of the personnel already assigned to operate the national meteorological services. Moreover, the private sectors of the four countries are not in a position to support the financing of the Hydromet project since most of the project's objectives fall under open access public services. It is not in the role of the private sector to take over the production of public services. There is therefore no risk of crowding out the private sector. The financial viability of the project is based on grant financing of investments. The absence of loan and therefore of obligation to repay capital and interest does not increase the burden of the public debt of the States, the ratios of public debts of the States are therefore not affected by the project funding. Finally – importantly – the four countries benefiting from the Hydromet project will be able to build sustainable, long-term business models from the reliable operation of strengthened hydrometeorological systems and recover the costs of operation and maintenance (O&M) from commercial revenues from sale of CP-CS, and through national budget support. The business model and the budget funding analysis (see Annex 3a) show that the impact of the Hydromet project will be easily handled by the four countries together, as the O&M costs of the new Hydromet equipment overall, on the budgets of the four beneficiary NHMSs, will be limited; these costs will be shared adequately among the RCC member countries, as per the RCC multi-lateral agreement signed between these countries under Activity 1.1.2 of the proposed project. Moreover, in the long term, development of commercial revenues will replace part of the current public funding of NMHS, from 30% to almost 50% of their budget. This indicates that the Hydromet project-related interventions will no more rely on international funding in the long term.

# LOGICAL FRAMEWORK

This section refers to the project/programme’s logical framework in accordance with the GCF’s Performance Measurement Frameworks under the Results Management Framework to which the project/programme contributes as a whole, including in respect of any co-financing.

E.1. Paradigm shift objectives

☐ Shift to low-emission sustainable development pathways ☒ Increased climate resilient sustainable development

| E.2. Core indicator targets |  |  |
| --- | --- | --- |
| E.2.1. Expected tonnes of carbon dioxide equivalent (t CO2 eq) to be reduced or avoided (mitigation and cross-cutting only) | Annual | Not applicable |
|  | Lifetime | Not applicable |
| E.2.2. Estimated cost per t CO2 eq, defined as total investment cost / expected lifetime emission reductions (mitigation and cross-cutting only) | (a) Total project financing; _____ Choose an item.. (b) Requested GCF amount; _____ Choose an item.. (c) Expected lifetime emission reductions; _____ t CO2eq. (d) Estimated cost per t CO2eq (d = a / c); _____ Choose an item. / t CO2eq. (e) Estimated GCF cost per t CO2eq removed (e = b / c); _____ Choose an item. / t CO2eq. |
| E.2.3. Expected volume of finance to be leveraged by the proposed project/programme as a result of the Fund’s financing, disaggregated by public and private sources (mitigation and cross-cutting only) | (f) Total finance leveraged; _____ Choose an item.. (g) Public source co-financed; _____ Choose an item.. (h) Private source finance leveraged; _____ Choose an item.. (i) Total Leverage ratio (i = f / b); _____. (j) Public source co-financing ratio (j = g / b); _____. (k) Private source leverage ratio (k = h / b); _____. |
| E.2.4. Expected total number of direct and indirect beneficiaries, (disaggregated by sex) | Direct | 6,054,909 50% female |
|  | Indirect | 13,398,377 50% female population is expected to be indirect beneficiaries |
|  | For a multi-country proposal, indicate the aggregate amount here and provide the data per country in annex 17. |  |
| E.2.5. Number of beneficiaries relative to total population (disaggregated by sex) | Direct | 21% of which 50% females |
|  | Indirect | 46% of which 50% females |
|  | For a multi-country proposal, leave blank and provide the data per country in annex 17. |  |

| E.3. Fund-level impacts |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Expected Results | Indicator | Means of Verification (MoV) | Baseline | Target |  | Assumptions |
|  |  |  |  | Mid-term | Final |  |
| A1.0 Increased resilience and enhanced livelihoods of the most vulnerable people, communities and regionsA1.0 Increased resilience and enhanced livelihoods of the most vulnerable people, communities and regions | A1.1 Change in expected losses of lives and economic assets (US$) due to the impact of extreme climate-related disastersA1.1 Change in expected losses of lives and economic assets (US$) due to the impact of extreme climate-related disasters | SWIO-RAFI study; Project Mid-term and Terminal reviews | Physical damages estimated at USD 13.4 billion | n/a | Gain in terms of avoided losses at USD 14 million | CP-CS are used by population and targeted sectors to inform decision-making processes The CP-CS produced bring actual benefits to communities and sectors |
| A2.0 Increased resilience of health and well-being, and food and water securityA2.0 Increased resilience of health and well-being, and food and water security | A2.2 Number of food secure households (in areas/periods at risk of climate change impacts)A2.2 Number of food secure households (in areas/periods at risk of climate change impacts) | Project Mid-term and Terminal reviews; Field surveys; governments/FAO stat. | Prevalence of food insecurity: - Comoros: 50% of pop. - Madagascar: 35% of households - Mauritius: 18.5% of population - Seychelles: 14.3% of pop. | +10% of the population is food secured in each target country | +22% of the population is food secure in each target country | Hydromet information is disseminated to end-users using appropriate channels and used to inform decision-making The CP-CS produced bring actual benefits to communities and sectors |

| E.4. Fund-level outcomes |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Expected Outcomes | Indicator | Means of Verification (MoV) | Baseline | Target |  | Assumptions |
|  |  |  |  | Mid-term) | Final |  |
| A5.0 Strengthened institutional and regulatory systems for climate-responsive planning and developmentA5.0 Strengthened institutional and regulatory systems for climate-responsive planning and development | A5.1 Institutional and regulatory systems that improve incentives for climate resilience and their effective implementationA5.1 Institutional and regulatory systems that improve incentives for climate resilience and their effective implementation | Assessment of regulatory frameworks of NMHS, of RFCS and NFCSs | Regulatory systems are not in place or inadequate | n/a | A strong institutional strategy is in place for each NMHS; a RFCS established at regional level and a NFCCS is developed for each country | NMHS are willing to participate to the development of, and to adopt regulatory frameworks and CP-CS |
| A6.0 Increased generation and use of climate information in decision-makingA6.0 Increased generation and use of climate information in decision-making | A6.1 Use of climate information products/services in decision-making in climate sensitive sectorsA6.1 Use of climate information products/services in decision-making in climate sensitive sectors | Survey among sectors and end-users | A baseline study of CP-CS use in each target country will be undertaken under Activity 1.4.1 | 1 additional key sectors from baseline use CP-CS in each country | 2 additional key sectors from baseline use CP-CS in each country | NMHS, DDR institutions and sectors work together to co-produce user-friendly CP-CS Sector authorities are willing to use the CP-CS developed |
| A7.0 Strengthened adaptive capacity and reduced exposure to climate risksA7.0 Strengthened adaptive capacity and reduced exposure to climate risks | A7.1 Use by vulnerable households, communities, businesses and public-sector services of Fund-supported tools instruments, strategies and activities to respond to climate change and variabilityA7.1 Use by vulnerable households, communities, businesses and public-sector services of Fund-supported tools instruments, strategies and activities to respond to climate change and variability | Surveys among selected communities and sectors | Use of fund-supported tools is 0 at baseline | 10% of target pop. (50% male and 50% female) | +46% of pop. (50% male and 50% female) | The CP-CS developed during the project are still being used/maintained beyond the project’s lifetime |
| A7.0 Strengthened adaptive capacity and reduced exposure to climate risksA7.0 Strengthened adaptive capacity and reduced exposure to climate risks | A7.2 Number of males and females reached by [or total geogrpahic coverage of] climate-related early warning systems and other risk reduction measures established/strengthenedA7.2 Number of males and females reached by [or total geogrpahic coverage of] climate-related early warning systems and other risk reduction measures established/strengthened | Surveys | A baseline study of CP-CS use in each target country will be undertaken under Activity 1.4.1 | +10% of the defined baseline (50% male and 50% female) | +40% baseline (50% male and 50% female) | Warnings reach relevant population using adequate dissemination channels |
| A8.0 Strengthened awareness of climate threats and risk-reduction processesA8.0 Strengthened awareness of climate threats and risk-reduction processes | A8.1 Number of males and females made aware of climate threats and related appropriate responsesA8.1 Number of males and females made aware of climate threats and related appropriate responses | Surveys | A baseline study of CP-CS use in each target country will be undertaken under Activity 1.4.1 | +10% baseline (50% male and 50% female) | +40% baseline (50% male and 50% female) | Interactions between CP-CS providers and end-users is effective, through the UIP, NCOF, SWIOCOF and other means |

| E.5. Project/programme performance indicators |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| The performance indicators for progress reporting during implementation should seek to measure pre-existing conditions, progress and results at the most relevant level for ease of GCF monitoring and AE reporting. Add rows as needed. |  |  |  |  |  |  |
| Expected Results | Indicator | Means of Verification (MoV) | Baseline | Target |  |  | Assumptions |
|  |  |  |  | Mid-term | Final |  |  |
| 1.1 A Regional Climate Centre and R/NFCS established | Number of RCC established Number of RFCS Number of NFCS | Review of the RCC strategies and of the frameworks | 0 | 1 RCC 1 RFCS 4 NFCS | 1 RCC 1 RFCS 4 NFCS 1 detailed regional business model | Partner countries agree on a strategy to set up each key component of the RCC, and to maintain the RCC functions beyond project’s lifetime |  |
| 1.2 Institutional arrangements and operational and financial strategy of NMHS strengthened | Number of NMHS institutional and operational strategies developed, including business models | Review of the strategies | 0 | 4 institutional strategies | 4 institutional strategies 4 detailed business models | Stronger institutions provide a adequate environment to generate profit and retain staff |  |
| 1.3 Improved staffing of the RCC, NMHS and other relevant institutions | Number of staff members recruited and trained | Surveys; review of training material and training attendance lists | 0 | 40 | 60 (at least 15 per country recruited and/or trained) | Skilled/trained staff is retained |  |
| 1.4 Detailed Design and System Integration of Project Activities | Number of system integration designed | Review of the system integration design | 0 | 4 | 4 | System integrator has been chosen in year 1 |  |
| 2.1 Enhanced hydro-meteorological observing, monitoring, and impact forecasting services | Number of network set up Number of information system established | Survey | 0 20 | 4 25 | 8 28 | From 20 existing systems along the four countries, at the end of the project 28 will be renewed or set-up |  |
| 2.2 Regional facilities for maintenance and training established | Number of facilities established or refurbished | Review of the facilities | 1 training center |  | 1 maintenance center 1 refurbished training center | Agreement is achieved at the regional level to provide for the facilities’ running cost beyond project’s lifetime |  |
| 2.3 R&D capacities enhanced to improve understanding of climate and disaster risks on communities and sectors | Number of staff trained on NWP downscaling Number of staff trained on dynamic downscaling and ensemble forecasts Number of staff trained on hydrology Number of staff trained on downscaling seasonal forecasts Number of hazard maps developed Number of vulnerability maps developed | Training attendance lists Review of hazard and vulnerability maps | 0 | 2 staff per country trained in each topic 1 multi-stakeholder workshop organised in each country to develop maps 1 hazard map developed in each country 1 climate vulnerability map developed in each country | 4 staff members trained in each country in each topic 3 multi-stakeholder workshops organised in each country At least 2 hazard maps and 2 climate vulnerability maps developed in each country | Trained staff members are retained in the NMHS Staff members of NMHS collaborate with DRR institutions and CP-CS users to increase risk understanding |  |
| 3.1 Production and dissemination of CP-CS improved | Number of CP-CS developed Number of people with improved access to EW Users’ satisfaction of the products received | Survey among population Survey in the agriculture, tourism and fisheries sector Review of the CP-CS | Number of people with access to improved CP-CS is 0 at baseline | Locally-relevant weather bulleting delivered daily + 20% baseline with improved EW access in each country + 20% baseline regarding users’ satisfaction | Locally-relevant weather bulleting delivered daily Agricultural advisories disseminated to farmers + 46% baseline with improved EW access in each country Baseline +46% regarding users’ satisfaction | NMHS and users collaborate to produce user-friendly CP-CS ; feedback loop is implemented |  |
| 3.2 Short- and long-term risk reduction and adaptation plans improved or developed | Number of national emergency response plans improved Number of local emergency response plans developed Number of adaptation policies updated | Review of the emergency plans Review of the adaptation policies | National emergency plans in place (with flaws) NAP under development National adaptation strategy (to be updated in Seychelles) | 4 national emergency response plans improved | 4 national emergency response plans improved 8 local emergency response plans developed 4 adaptation plans/strategy updated | NAPs are ready to be updated (after 5 years of development) |  |
| 3.3 Training and improved communication with users and end-users of CP-CS established | Number of staff members of NMHS trained to package CP-CS according to users’ needs Number of users trained to use CP-CS Number of interaction platform enhanced Users’ satisfaction of UIP and SWIOCOF Number of users attending SWIOCOF | Review of training programme and attendance list Surveys among users Review of SWIOCOF attendance list | 1 UIP to be strengthened SWIOCOF to be strengthened | + 20% baseline regarding users’ satisfaction | 1 UIP strengthened 1 SWIOCOF per yr with active participation of users Baseline +50% regarding users’ satisfaction of the UIP and SWIOCOF Baseline +50% regarding users’ attendance to SWIOCOF | The UIP and SWIOCOF provide products that respond to users’ needs |  |

| E.6. Activities |  |  |  |
| --- | --- | --- | --- |
| Activity | Description | Sub-activities | Deliverables |
| 1.1.1 Develop regional and national frameworks for climate services (RFCP-CS & NFCP-CS) | The RFCS will be developed based on the WMO GFCS and serve as an umbrella under which each partner country will develop its own national framework for climate services. The RFCS will include the following elements: - a common regional methodology and rule book (based on international WMO standards) for weather monitoring, forecast and climate monitoring for long term prediction at regional and downscaled level, relevant to the nature of hazards and resilient responses. - regional protocols to disseminate weather- and climate-forecasts to relevant users and provide decision makers with the information they need for long time planning. - a protocol for member countries to ensure a systematic collection and integration of user feedback to co-produce and improve climate services. - A draft profile of a RCC which will be established under Activity 1.1.2. The RFCS will also promote the role of the UIP and SWIOCOF (to be strengthened under Activities 3.3.3 & 3.3.4) as communication platforms to disseminate regional climate products developed by the RCC, national climate products developed by the NMHS, and to facilitate communication and knowledge exchange among the RCC member countries. Based on the RFCS, NFCS in the four target countries will be developed (none existing currently). These frameworks will also promote NCOFs as complementary forums to SWIOCOF/SARCOF in terms of calendar and content/activities. National frameworks will follow the broad guidelines from the RFCS – especially to harmonize process and equipment for climate data monitoring among countries – but be country-specific. Ultimately, the RFCS and NFCS will contribute to develop a common risk culture in the IOC region that reinforces weather data and information sharing in order to better understand and monitor main hazards for the region (i.e. cyclones, storms with heavy wind and heavy rain). | 1.1.1.1 Organise consultations with stakeholders in IOC, NMHSs, DRR institutions, climate sensitive sectors to develop the RFCS. 1.1.1.2 Organise a regional workshop to validate the RFCS. 1.1.1.3 Once the RFCP-CS is validated, design the NFCS following the guidelines of the RFCS. 1.1.1.4 Organise 4 national workshops to present and validate the NFCS in Comoros, Madagascar, Mauritius and Seychelles. Responsible parties: - Leader: IOC with the Support of PMU expertise to recruit an expert (meteorologist/climate services expert) - Beneficiary supervision and validation: RCC and NMHS - Stakeholders to be involved and consulted: DRR institutions, climate sensitive sectors | RFCS and NFCS |
| 1.1.2 Design the legal, institutional, financial and organisational strategy to establish the RCC within IOC | RCCs, established according to WMO standards, are centres of excellence, holding regional responsibilities (not to duplicate or replace the responsibilities of NMHS). RCCs typically develop regional climate products, as well as implement training and capacity building interventions at the regional scale. The climate products include long-range forecasts which can be used as decision-making tools for climate change adaptation and disaster risk reduction. With these products, countries in the RCC region are able to deliver better climate services to national users. The RCCs constitute integral components of WMO's Global Data Processing and Forecasting System (GDPFS) underpinning the generation of climate information products by the NMHSs. The RCC will be established under the aegis of IOC. Based on the RCC profile prepared under Activity 1.1.1, a complete strategy to establish the RCC of the SWIO region will be developed, based on WMO guidelines to establish RCC; and based on an analysis of strategies of other existing RCC, to identify legal, institutional and financial settings that would better suit the targeted region. The RCC strategy will confirm and define the details of the following regional elements : - Which country will have the administrative and logistic responsibilities for the RCC, under the aegis of IOC; - IOC’s role in the organisation of the SWIOCOF every year will be strengthened; - technical expertise and responsibilities to prepare climate products will be shared between RCC and member countries. For regional products, a ‘regional expert team’ will be set up, composed of selected hydro-meteorologists from the RCC member states. The RCC established under this activity will provide the following regional services and facilities to IOC member states: i) regional training and capacity building in the 2 training centers of the region region – one to be established under the proposed project (Activity 2.2.1); ii) calibration and maintenance services for the hydro-meteorological equipment (Activity 2.2.2); iii) production of user-tailored, long-range climate products to benefit key climate-sensitive sectors (see Activity 2.3.2); iv) dissemination of these long-range products within member states via the UIP and SWIOCOF (Activities 3.3.3 & 3.3.4); and v) experience and knowledge sharing for adaptation and risk reduction via SWIOCOF and the UIP. Key sectors in the beneficiary countries members of the RCC will be able to use the climate products, prepared by the RCC, as decision-making tools to develop climate-resilient strategies and guide investments. This will be done by ensuring that the climate products developed within the RCC – either at IOC level or in a specific NMHS of the region with the relevant equipment and expertise (to be determined in the RCC strategy) – are co-produced with users in climate-sensitive sector and national sectoral experts (e.g. agronomist to develop agro-meteorological bulletins) – see Output 2.3. The RCC strategy will also identify if new staff members should be recruited to run the RCC; and, if so, how they will be paid in the long term (see below). RCC staff members will receive basic trainings on CP-CS under Activity 1.3.2. Once the RCC strategy is approved by all member states and IOC, through multi-lateral agreement, they will also agree on how each member state will financially contribute to the running costs of the RCC beyond the project’s lifetime – e.g. finance for the maintenance laboratory, training center (Activity 1.1.3), sharing O&M costs of the hydrometeorological equipment, sharing costs of UIP (Activity 3.3.3) and SWIOCOF (Activity 3.3.4). A regional business model will also be developed to identify additional sources of funding for the RCC from public and private sectors through sale of regional CP-CS (see Annex 3a). | 1.1.2.1 Design the RCC’s strategy, based on WMO standards for Climate Centers, in collaboration with IOC and RCC future member states. The strategy will include type and number of staff members needed, roles and responsibilities of the RCC, membership specificities for meteorological services and definition of their relation to the RCC, etc.- 1.1.2.2 Organise a validation workshop with IOC and the proposed member states of the RCC to validate the proposed strategy and institutional organigramme, as well as regional services to be delivered by the RCC (e.g. equipment calibration and maintenance). At the end of the workshop, a multi-lateral agreement will be reached between IOC and RCC member states. 1.1.2.3 Develop a business model/cost-recovery plan that underlines how the regional services – agreed upon under sub-activity 1.1.2.2 – will be financed from national contributions and other potential sources. 1.1.2.4 Present and validate the ‘regional business model’ of the RCC during a participative workshop. Responsible parties: - Leader: IOC with the Support of PMU expertise to recruit an institutional/legal expert and an economist - Beneficiary supervision and validation: IOC and meteorological services of the RCC member countries - Stakeholders to be involved and consulted: meteorological services of the RCC member countries | 1 RCC |
| 1.1.3 Design the strategy of the regional laboratory for maintenance and annual calibration of equipment, and the strategy of the regional training center | A strategy to set up a calibration and maintenance laboratory will be developed, especially to determine where the laboratory should be established, how it will be run and funded (by consulting all countries), and what equipment will be needed to maintain and calibrate the hydromet equipment of the region, including those provided under Output 2.1. Moreover, a strategy to strengthen and improve operationalisation of the training center (currently based in Mauritius) will be developed, ensuring that training performed in Mauritius is complementary to training performed in La Reunion. | 1.1.3.1 Review existing training center strategy and equipment and identify gaps 1.1.3.2 Work with IOC and the staff members of the meteorological services in the four countries to design/strengthen strategies of the maintenance lab and training center. Responsible parties: - Leader: IOC with the Support of PMU expertise to recruit 2 experts specialised in maintenance & operation of observing networks; and hydro-meteorology training working with IOC and NMHSs - Beneficiary supervision and validation: NMHS Stakeholders to be involved and consulted: meteorological services and staff members of the training center in La Reunion |  |
| 1.1.4 Prepare a strategy to improve Regional Numerical Weather Prediction | This strategy aims to ensure the harmonization of climate products across countries, based on international WMO standards. This strategy will be done at the regional level for the RCC to define a global view of NWP. However, the output of the NWP will be used at national level in the countries to improve the climate services they produce and disseminate within their territories. | 1.1.4.1 Prepare a regional strategy to improve Numerical Weather Prediction, in collaboration with representatives of the national meteorological services of each country and external expertise as needed (e.g. Météo-France La Réunion). 1.1.4.2 Design the down scaling strategy for each country including the computing facilities. 1.1.4.3 Organise a regional workshop with the representatives of the national meteorological services of each country and Météo-France La Réunion to validate the strategy. Responsible parties: - Leader: IOC with the Support of PMU expertise to recruit a consultant (meteorologist) - Beneficiary supervision and validation: IOC and meteorological services in each country Stakeholders to be involved and consulted: IOC and meteorological services |  |
| 1.2.1 Strengthen the institutional, operational and financial strategy of NMHSs for each target country | The purpose of the strategy is to improve efficiency within NMHSs with particular attention given to retaining skilled staff (hired and/or trained under this project). For this, institutional settings will be improved in order to streamline the role and responsibilities of staff members (existing and newly hired under Activity 1.3.3). The strategy will also strengthen the operationalisation of NMHS to meet WMO’s requirements for category 3 NMHS. For example, FS, Chapter 3 indicates the following needs to be addressed: - establish a formal written governance structure for DGM (Madagascar) and ANACM (Comoros); - ensure participation of the NMHS in research projects (4 countries – to be done under Output 2.3); - established procedure to collect users’ feedback on CP-CS (4 countries – to be done through the NFCS and UIP); and - improve dissemination of forecasts and national observations on website (4 countries – to be done under Component 3). All these elements will be included in the NMHS strategy and implemented under Component 1, 2 and 3 of the proposed project. Other recommendations from the FS point to the need for capacity building and staffing - which will be addressed under Activity 1.3.1 and 1.3.2. The institutional strategy will also strengthen the collaboration between meteorological, hydrological, DRR services and sectoral ministries and provide guidelines for NMHS’ contribution to the production of climate-related policies and strategies. As part of this strategy, an in-depth analysis of cash flow will be performed to develop a business model with a cost-recovery plan for each NMHS. The business-model is key to ensure the long-term maintenance of the NMHS, the use/sustainability of new equipment and software (maintenance cost, license renew), and yearly organisation of NCOF (which are promoted in the NFCS developed under Activity 1.1.1). The business model will take into account economic growth/avoided costs expected through the project in climate-sensitive sectors (see Economic Analysis Annex 3a); it will also identify sources of funding for the NMHS through public fund and sale of CP-CS. | 1.2.1.1 Update the capacity assessment conducted in Annex 2 (FS, Chapter 3) 1.2.1.2 Investigate through consultations with relevant stakeholders the collaboration between met, hydro, and DRR services and identify pathways to increase collaboration and improve communication 1.2.1.3 Analyse cash-flows within NMHS and national markets to identify potential buyers of CP-CS and willingness to pay, price elasticity (in public and private sector), as well as other sources of finance to support the production of CP-CS in the long-term. 1.2.1.4 Develop, present and validate the recommendations for institutional and financial strengthening with a business model that is aligned with each country’s reality/context – e.g. from centralised to decentralised models – during 4 national workshops. Responsible parties: - Leader: IOC with the Support of PMU expertise to recruit 1 institutional expert and 1 economist - Beneficiary supervision and validation: the NMHS of each country Stakeholders to be involved and consulted: NMHS, stakeholders from the private sectors | Robust institutional strategies with detailed business and cost-recovery plans for each NMHS |
| 1.2.2 Design the transition support plan of each NMHS, DRR institutions and relevant sectoral ministries | The transition support plans are developed to prepare, support, and help individuals, teams, and organizations (met. services and main stakeholders) in the implementation phaseof the proposed project; these plans will enable organizational change based on the needs required by the project. For the purpose of Hydromet project, the plans will be developed for the meteorological and hydrological services, DRR institutions and sectoral ministries in GFCS priority areas, in all 4 target countries. | 1.2.2.1 Define measurable stakeholder gains (inside and outside the met services) through consultations with these stakeholders, and create a roadmap for their achievement 1.2.2.2 Track assumptions, risks, dependencies, costs, returns on investment, dis-benefits and cultural issues 1.2.2.3 Organise workshops to inform various stakeholders of the reasons for the change, the benefits of successful implementation, as well as a detailed plan of what the changes will entail of the change and their key role in the process. 1.2.2.4 Design an effective education, training and/or skills upgrading scheme for the organisation (transition support plans) Responsible parties: - Leader: IOC with the Support of PMU expertise to recruit 1 expert in production and sale of CP-CS (e.g. from MF, UKmet, etc.) - Beneficiary supervision and validation: NMHS in each country Stakeholders to be involved and consulted: NMHS and DRR institutions in each country |  |
| 1.3.1 Recruit new staff members for the RCC and meteorological services | Staffing needs will be identified for each meteorological service, and has been identified for the RCC under Activity 1.2.1. For example, the FS identified the need for meteorological services to hire more staff with MSC’s and PhD’s to meet the requirements of WMO NMHS Category 3. If new staff is to be recruited – which will be decided by each NMHS at project onset –, it would require commitment and investment from national government to sustain the positions beyond project completion. | 1.3.1.1 Assess staffing needs for the RCC and in each meteorological services to contribute to the production of improved and new weather/ seasonal forecasts and climate projections. 1.3.1.2 National meteorological services and IOC recruit new staff members (if needed) with required expertise Responsible parties: - Leader : IOC with the Support of PMU expertise to recruit a consultant (hydromet expert) - Beneficiary supervision and validation : IOC/RCC and meteorological services to be nominated for each country Stakeholders to be involved and consulted: IOC and meteorological services to be nominated for each country for need assessment |  |
| 1.3.2 Train/update training for new/existing staff | The training will cover basics on climate services, risk prediction models, and risk exposure of population and sectors; with regards to risk exposure, the training will use the hazard maps and vulnerability assessments prepared under Activities 2.3.5 and 2.3.6. The training will not only target staff members of the meteorological services and RCC, but also staff in hydrology services, in DRR and climate-sensitive sectors of the GFCS. It will be implemented by national/regional universities, research institutions and academics with a priority given to those located within or nearby the SWIO region (e.g. Indian Ocean-based consultants working on RIMES). | 1.3.2.1 Identify relevant training programmes in national/regional institutions 1.3.2.2 Train existing staff within these programmes. Responsible parties: - Leader : IOC with the Support of PMU expertise to recruit a consultant (hydromet expert); national or regional universities/research center/academics etc. to conduct basic trainings - Beneficiary supervision and validation : RCC, NMHS, DRR institutions and climate-sensitive sectors of the GFCS Stakeholders to be involved and consulted: RCC, NMHS, DRR institutions and climate-sensitive sectors of the GFCS for training need assessment |  |
| 1.4.1. Conduct baseline studies on CP-CS use in each beneficiary country | The studies will be conducted to assess access to, and use of CP-CS at baseline in the following sectors: agriculture and fisheries (Comoros and Madagascar); agriculture and tourism (Mauritius); fisheries and tourism (Seychelles); as well as access to early warnings for cyclones and other extremes in all countries. This will build understanding of current CP-CS outreach in each target countries, and how these are used, in order to inform the development of the detailed system (1.4.2) as well as to identify pathway to increase CP-CS outreach through the proposed project. Baseline levels will be re-assessed at project mid- and end-term to demonstrate changes achieved through the project. | 1.4.1 Conduct surveys in each country to assess access to CP-CS Responsible parties: - Leader : IOC with the Support of PMU expertise to recruit a consultant (hydromet expert); - Beneficiary supervision and validation : NMHS Stakeholders to be involved and consulted: NMHS, DRR institutions, climate-sensitive sectors of the GFCS and targeted communities/private sector stakeholders receiving/using CP-CS |  |
| 1.4.2. Produce a detailed design and system integration for each NMHS | This activity will include the development of the detailed system integrating all project activities, the preparation of an implementation plans and technical specifications and tender documents for equipment and services. The systems integration will help to develop new information products and services, and operationalizing their production. Implementation support will be provided to NMHS team for effective functioning of the global system. In addition, the system integration will ensure functional compatibility of the modernized meteorological and hydrological systems with the global/regional systems as recommended by WMO and with the existing systems installed at each NMHS. | 1.4.2.1 Detail the design of each piece of the system with at least: Global data, Local observation, Telecom system, Data check and storage, Numerical Weather Prediction (NWP), Forecaster system, Climatology, End-user’s production, Dissemination, 1.4.2.2 Prepare the technical specification of the different systems to be procured Responsible parties: - Leader : IOC with the Support of PMU expertise to recruit a firm (specialised in provision of hydro-meteorological equipment) which will be responsible for Activity 1.4.1; 1.4.2; 2.1.1; and 2.1.2) - Beneficiary supervision and validation : NMHS in each country Stakeholders to be involved and consulted: NMHS in each country |  |
| 1.4.3 Ensure full system integration from observation stations to delivery of CP-CS to end-user | This activity includes the development of step-by-step practices and procedures for system integration and coordination of project activities. The observation and monitoring network and remote sensing equipment will be modernised/ completed with harmonized equipment for all met services to facilitate information exchange (Activity 2.1.1). In addition, IT systems will be upgraded accordingly with WMO standards (Activity 2.1.2). It is expected that this activity will include the active participation of experts from developed NMHS, which are directly involved or well familiar with operational aspects of production and service delivery of meteorological and hydrological products and actively involved in the development of WMO programs. | 1.4.3.1 Conduct capacity gap analysis of IT system in each country 1.4.3.2 Design the proper technical integration of the different systems from previous activity to make the global system as efficient as to disseminate services including: Data exchange, Product and services exchange, MoU between institutions to contract on data and services Responsible parties: - Leader : IOC with the Support of PMU expertise to recruit a firm (specialised in provision of hydro-meteorological equipment) which will be responsible for Activity 1.4.1; 1.4.2; 2.1.1; and 2.1.2) - Beneficiary supervision and validation: NMHS in each country Stakeholders to be involved and consulted: NMHS in each country |  |
| 2.1.1 Modernise/upgrade climate observation and monitoring network | The observation and monitoring network and remote sensing equipment in each NMHS will be modernised/ completed with harmonized equipment for all to facilitate information exchange. The reinforcement will follow WMO standards; equipment linked to hydrology – in particular to monitor rainfall in water catchments – have been identified through the HYCOS study (see corresponding Annex 22) and, for Mauritius, also through the ER2C project. In Madagascar, the hydrological equipment will be established to complement what has been set up under Project PACARC and the future UNDP-GCF ‘Hydromet Madagascar’ project. | Modernise/upgrade the networks based on the detailed strategy produced under output 1.4 2.1.1.1 In Comoros: Rehabilitation/extension of the building where the meteorological service is based, upgrade national synoptic networks (hydrologic stations following HYCOS recommendation), Sub synoptic rain network in flooding areas, Agrometeorological observing network, AWOS, Wave buoy, Upper air system, Doppler radar, Tower for radar 2.1.1.2 In Madagascar: Upgrade national synoptic networks (hydrological stations following HYCOS recommendations), Sub synoptic rain network in flooding areas, Agrometeorological observing network, Upper air system, Doppler radar, Tower for radar 2.1.1.3 In Mauritius: Upgrade national synoptic networks (AWS and hydrological stations following HYCOS recommendation), Sub synoptic rain network in flooding areas (Port-Louis), Wave radar for North Mauritius, Rodrigues and Agalega, Maregraph for North Mauritius, Rodrigues and Agalega and Brandon, Lightning network station at Rodrigues, Upper air system for Agalega, Saint Brandon and Rodrigues, Doppler radar for Rodrigues, Tower for radar 2.1.1.4 In Seychelles: Upgrade national synoptic networks (AWS and hydrological stations following HYCOS recommendations), Sub synoptic rain network in flooding areas (Mahé, Praslin and La Digue), Wave radar for Mahé, Praslin and La Digue, Maregraph for Mahé, Praslin and La Digue, Lightning network stations for Mahé, Praslin and La Digue, Doppler radar for Mahé, Tower for radar Responsible parties: - Leader : IOC with the Support of PMU expertise to recruit a firm (specialised in provision of hydro-meteorological equipment) which will be responsible for Activity 1.4.1; 1.4.2; 2.1.1; and 2.1.2) - Beneficiary supervision and validation : NMHS in each country Stakeholders to be involved and consulted: NMHS in each country | New/upgraded hydro-meteorological equipment in the four target countries |
| 2.1.2 Modernise/upgrade information system for telecom, forecast, climatology | Based on a capacity gap analysis, modernize/upgrade the IT systems accordingly to WMO standards. | In the four countries the following systems will be updated and/or set-up by the firm hired under Activity 1.4.1 working with NMHS: 2.1.2.1 Data collecting system 2.1.2.2 Automatic Meteorological Switching System 2.1.2.3 Computing centre 2.1.2.4 Storage and archive of national data 2.1.2.5 Forecaster workstation 2.1.2.6 Climatological Database Management System 2.1.2.7 End user production system Responsible parties: - Leader : IOC with the Support of PMU expertise to recruit a firm (specialised in provision of hydro-meteorological equipment) which will be responsible for Activity 1.4.1; 1.4.2; 2.1.1; and 2.1.2) - Beneficiary supervision and validation : NMHS in each country Stakeholders to be involved and consulted: NMHS in each country | New/upgraded information systems |
| 2.2.1 Establish a maintenance and calibration laboratory | A regional maintenance laboratory will be built and equipped to do support maintenance work and calibration on the new acquired hydromet equipment, following the strategy developed under Activity 1.1.3. This will serve to avoid current extra cost sending the sensors or other equipment with a limited lifetime and in need of regular maintenance overseas for maintenance (typically Kenya or South Africa at present). | 2.2.1.1 Build the laboratory based on strategy developed under Activity 1.1.3 2.2.1.2 Provide all equipment that are required based on the laboratory strategy and gap analysis developed under Activity 1.1.3 Responsible parties: - Leader : IOC with the Support of PMU expertise to recruit a firm (specialised in provision of hydro-meteorological equipment) which will be responsible for Activity 1.4.1; 1.4.2; 2.1.1; and 2.1.2) ; and a firm for building the building - Beneficiary supervision and validation: NMHS in each country Stakeholders to be involved and consulted: NMHS in each country | 1 regional calibration center |
| 2.2.2 Refurbish regional training center of Mauritius to train observers and forecasters | The training center will be complementary to the existing training center in La Reunion. It will be upgraded following the strategy developed under Activity 1.1.3. | 2.2.2.1 Buy and install relevant equipment, for example, forecaster workstation and telecom system to train forecaster (to be determined in the laboratory strategy developed under Activity 1.1.3) Responsible parties: - Leader : IOC with the Support of PMU expertise to recruit a firm (specialised in provision of hydro-meteorological equipment) which will be responsible for Activity 1.4.1; 1.4.2; 2.1.1; and 2.1.2) - Beneficiary supervision and validation : NMHS in each country Stakeholders to be involved and consulted: NMHS in each country | 1 refurbished training center |
| 2.3.1 Organise training to improve downscaling of meteorological data and impact-based forecasts. | This activity will serve to improve the production of short-term ‘day-to-day’ forecasts and alerts in each target country (see Activity 3.1.1). Moreover, staff members of NMHS will be trained to produce impact-based forecasts (IBF) to translate hydromet hazards into sector and location-specific impacts. This is key to enable mitigation response from the government. Both daily forecasts and IBF will benefit from high-quality data which are produced and collected with the equipment established under Activity 2.1.1 and 2.1.2. | 2.3.1.1 Conduct dynamic downscaling of numerical weather prediction using Limited Area Model (LAM) like Arome or WRF to get a spatial resolution of about 1km. These LAM will use assimilation techniques to use the new observing data acquired through Activity 2.1.1 2.3.1.2 Conduct statistical downscaling using Artificial Intelligence techniques (deep learning) to adapt the numerical weather prediction combining them with observing data with IoT data analytic capability 2.3.1.3 Conduct training on the importance of IBF to understand hazards’ impacts on sectors and locations Responsible parties: - Leader : IOC with the Support of PMU expertise to work with relevant experts (e.g. existing staff of training laboratory in La Reunion and Mauritius) - Beneficiary supervision and validation : meteorological services in each country Stakeholders to be involved and consulted: meteorological services in each country |  |
| 2.3.2 Organise training and R&D activities on climate modelling capacity | R&D activities like regional downscaling and national calibration of the different models will be performed at regional level with representatives of each country’s meteorological services. The production of downscaled climate change models will use BRIO outputs and be based on BRIO methodologies. Based on the downscaled climate change models, sectoral models and impact assessments will be prepared to anticipate climate change impacts in each country. The climate change models and projections as well as the sectoral models and impact assessments will be shared on the UIP. The implementation of these downscaled and sectoral models will be done at national level under component 3. | 2.3.2.1 Produce atmospheric models using dynamic downscaling and ensemble forecast 2.3.2.2 Produce downscaled climatic change models with ensemble forecast at country level based on the regional models produced under BRIO 2.3.2.3 Share downscaled forecasts and CC predictions on the online platform 2.3.2.4 Produce sectoral models and impact assessments to anticipate the climate impacts in each country (e.g. urban hydrology, pollution, agrometeorology, sea state, coastal erosion) Responsible parties: - Leader : IOC with the Support of PMU expertise to work with relevant experts (e.g. staff of training laboratory in La Reunion and Mauritius) - Beneficiary supervision and validation : meteorological services in each country Stakeholders to be involved and consulted: meteorological services in each country |  |
| 2.3.3 Organise training on hydrological modelling for flood prevision (i.e. flood propagation model) | Annex 2, the FS, Chapter 3 has identified gaps in monitoring hydrology data, hydrology expertise and predicting floods in the four target countries. This is also underlined in the HYCOS study (Annex 22). Hence, the training will target the staff members of the national hydrological services in the four target countries. The purpose of the training is to: i) improve knowledge of hydrological processes in water catchments; ii) improve knowledge of different types of flood that can occur on different types of water catchments; iii) monitor flood risk on key water catchments using the hydrological equipment established under Activity 2.1.1; iv) understand how to set up a flood risk alert system for one/several specific water catchments (which will be set up under Activity 3.1.2); v) understand urban flood risks based on IDF curves; and vi) learn how to produce flood hazard maps and flood vulnerability assessments (see Activity 2.3.5 and 2.3.6). | 2.3.3.1 Design and implement relevant training in one of the regional center or at national level Responsible parties: - Leader : IOC with the Support of PMU to recruit hydrologist - Beneficiary supervision and validation : hydrological services in each country Stakeholders to be involved and consulted: hydrological services in each country |  |
| 2.3.4 Organise training to produce seasonal agrometeorological bulletins downscaled at national, regional and local level (if possible) | Annex 2, the FS, Chapter 3 has identified gaps in producing seasonal agrometeorological forecast at local level especially for Comoros, Madagascar and Mauritius, where agriculture is key for the economy. This activity will serve to downscale the production of seasonal forecast by: - training experts of the target countries to develop skills in the downscaling of the global seasonal forecasts. - defining and generating by countries' experts climate products or services from datasets created (in line with the needs of national users). - providing countries in the region with high-resolution regional seasonal forecast. In Madagascar, the training will use the methodologies and complement the PrAdA project (see baseline projects). The forecasts will be packaged according to users’ needs and disseminated under Activity 3.1.1. | 2.3.3.1 Develop specific training for agrometeorologists and implement it Responsible parties: - Leader : IOC with the Support of PMU expertise to work with relevant experts (e.g. existing staff of training laboratory in La Reunion and Mauritius) - Beneficiary supervision and validation : meteorological services and agriculture sector in the target countries Stakeholders to be involved and consulted: agriculture services in each country |  |
| 2.3.5 Develop hazards maps (cartes d’aléas) | As a base to improve climate risk understanding among staff members of NMHS, DRR institutions (with technical support from institutions in charge of hydrology and hazard maps) and CP-CS users, and to serve as decision-making tools for disaster risk reduction and climate change adaptation (see Component 3), hazard maps, which take into account climate change impacts on return period/intensity of selected hazards, will be produced in selected areas of the four target countries. The production of the maps will rely on enhanced climate and weather monitoring (Activity 2.1.1) and improved, downscaled climate change projections (2.3.2). As rainfall induced floods are significant throughout the SWIO region (related to tropical cyclones or not), flood risk maps will be prepared for the four countries, focusing on selected vulnerable areas. In Mauritius, this process will build on ER2C and the Land Master Plan initiatives (see Baseline projects) and complement the flood maps developed by LDA and Audit of Rivers (Min. Envir) under these 2 initiatives. In addition to floods, the following maps will be produced: - droughts for Comoros (relevant to agriculture in Anjouan) and Madagascar (also relevant to agriculture); and - coastal erosion for Mauritius and Seychelles (relevant to tourism and urban development planning). The hazard maps will serve to indicate the location, frequency (probability of occurrence taking into account climate change) and intensity of hazards. These maps will be useful to develop risk prevention plans (see Component 3). The maps will be produced by the NMHS with technical support from institutions in charge of hydrology and hazard maps, and shared regionally on the UIP (see Activity 3.3.3). | 2.3.5.1 Integrate or review existing hazard maps (if existing) 2.3.5.2 Identify areas most affected by the selected hazard in each country based on existing maps (if any), consultations with relevant stakeholders, scientific sources, etc. 2.3.5.3 Conduct consultations with stakeholders and community members in these areas to understand frequency and intensity of selected hazards 2.3.5.4 Develop or update hazard maps using the monitoring equipment established under Activity 2.1.1, and based on return period of the hazards taking into account climate change impacts, and based on stakeholder consultations conducted under 2.3.5.3 2.3.5.5 Present and validate the maps during national workshop 2.3.5.6 Share maps on the UIP established under activity 3.3.3. Responsible parties: - Leader : IOC with the Support of PMU expertise to recruit a hydro-meteorologist/climate change experts (1 consultant per country) - Beneficiary supervision and validation : NMHS and DRR institutions in each country - Stakeholders to be involved and consulted: NMHS and DRR institutions and sectors in each country | 2 hazard maps per country |
| 2.3.6 Develop climate vulnerability maps | Based on the hazard maps produced under Activity 2.3.5, a mapping exercise for climate-risk vulnerability – of people and assets – will be conducted in a participative way with the NMHS, local authorities of risk-prone areas, public and private sector representing agriculture/fisheries, tourism, health, water sectors and at-risk communities. The purpose will be to identify main assets and most vulnerable people affected by the selected hazards (selected under Activity 2.3.5) from a local point of view and based on how people/assets were affected during past events. This all-inclusive process will draw on local experiences and perspectives in order to capture current risks; such process will also contribute to awareness-raising among diverse stakeholders and encourage their involvement in DRR processes (including through the provision of feedback on climate products). Once the vulnerability assessments and maps are finalized and validated, training will be implemented for NMHS, stakeholders from climate-sensitive sectors and local authorities in the selected vulnerable areas for which the maps were developed to raise understanding of risk exposure at the local level, and future risks taking into account climate change projections (downscaled under Activity 2.3.2). The hazard maps will be useful to inform the NAP development process in the four countries, or their update (see Activity 3.2.2.). | 2.3.6.1 Conduct vulnerability assessments in areas most affected by selected hazards (at least 2 areas per country) 2.3.6.2 Develop vulnerability maps 2.3.6.3. Organise workshops to raise awareness of climate-related vulnerability and shifts in the context of climate change 2.3.6.4 Share maps on the UIP established under activity 3.3.3. Responsible parties: - Leader: IOC with the Support of PMU expertise to recruit a climate change expert - Beneficiary supervision and validation: NMHS, DRR institutions and sectors in each country - Stakeholders to be involved and consulted: NMHS, DRR institutions, sectors and vulnerable communities in each country | 1 climate vulnerability map per country |
| 3.1.1 Set up protocol to produce and deliver improved daily weather bulletin, impact-based forecasts, seasonal forecasts, and agricultural advisories | The FS (Annex 2, Chapter 3) has identified needs to improve the production and delivery of weather bulletin, IBF, seasonal forecasts, and other weather products among the population of the four target countries. This activity will improve the production and delivery of weather forecasts, which are used by all for ‘everyday life’ in the four target countries, and IBF which support risk prevention. The accuracy of these forecasts will be enhanced, thanks to a production of high-quality climate data, under Outcome 2. Under this activity, staff members of the national meteorological services – which has been trained under activity 2.3.1 for the downscaling of meteorological data and production of IBF – will receive support from a communication expert to prepare, package and disseminate their forecasts using relevant communication channels – including television, radio, and the website of the meteorological services - to ensure user-friendly format and wide outreach. In addition, in Comoros (Anjouan), Madagascar and Mauritius (where agriculture is a key activity – see Annex 2, FS, Chapter 1, and Annex 3a, Economic Analysis), agricultural advisories will be prepared by staff members of the meteorological services – trained under Activity 2.3.4 –, the ministry of agriculture, and representatives of farming communities to provide feedback on the format of the advisories and best communication channels. Where possible, the project will build on existing initiatives like PrAdA in Madagascar, by diversifying the type of crops for which agricultural calendars are produced, by upscaling success and by diversifying communication means used to disseminate agricultural advisories. | 3.1.1.1 Conduct surveys among population to identify best ways to package/prepare the forecasts to be disseminated among the public in each country . 3.1.1.2 Identify best packaging format and communication channels in each country – including TV, radio, newspaper – through surveys among population in particular farmers in Comoros, Madagascar and Mauritius, fishermen in Comoros and Seychelles, and the tourism industry in Seychelles and Mauritius. 3.1.1.3 Support the national meteorological services to format their forecasts adequately for each communication channel – using local languages as appropriate. 3.1.1.4 Prepare agricultural advisories through a participative process 3.1.1.5 Identify best communication channels and language/ format for farmers in Comoros, Madagascar and Mauritius 3.1.1.6 Disseminate the advisories using best communication channels 3.1.1.7 Disseminate all weather bulletins and advisories on the UIP to collect users’ feedback Responsible parties: - Leader: IOC with the Support of PMU expertise to recruit a communication consultant - Beneficiary supervision and validation: meteorological services and ministry of agriculture in each country Stakeholders to be involved and consulted: meteorological services and population including farmers (for surveys on packaging information and bets dissemination channels) in each country | Agricultural advisories |
| 3.1.2 Set up protocol to strengthen early warning dissemination for key sectors and among the general public | Thanks to the equipment installed under Component 2, NMHS will be able to forecast climate-related hazards earlier and more accurately. This activity will focus on improving alerts for climate-related risks in the four target countries. A presentation and assessment of how alerts are currently disseminated to vulnerable sectors (of the GFCS areas) and to the general public has been conducted in Annex 2, the FS, Chapter 2 and 3. The assessment underlines problems to issue timely warnings, that have a wide outreach in the four target countries (see Case Studies in Chapter 3 for concrete examples). To address this problem, end user’s in-depth analysis will be performed at national scale in each country to ensure the perfect adequacy between needs and solutions while packaging EW. In particular, consultations will be organised with vulnerable socio-economic groups in each country to identify best communication means to disseminate warnings – including cellphone, radio and trusted local stakeholders/leaders. Once channels have been identified, stakeholders e.g. at radio or national TV, or even community leads will be trained to disseminate user-friendly warnings in local languages. In addition to strengthening early warning for cyclones in the four target countries to ensure a wider outreach, the following early warnings will be established or strengthened, to target these specific groups: - in Comoros: EW for farmers and fishermen (using specific communication channels to reach these groups) focusing on heavy rainfalls (complementing and building on ‘Ensuring climate resilient water supplies in the Comoros islands’ UNDP-GCF project) and storms - in Madagascar: EW for farmers and fishermen (using specific communication channels to reach these groups and building on PrAdA in Madagascar) focusing on heavy rainfalls and storms - in Mauritius: EW for farmers and stakeholders in the tourism and health (using specific communication channels to reach these groups – based on methodologies and outputs from project SAWIDRA for health) focusing on heavy rainfalls, heat waves and storms - in Seychelles: general public and stakeholders in tourism for heavy rainfalls and storms (e.g. through cell phone app); specific warnings for fisheries for storms and algal blooms (building on IAEA ‘Monitoring of Algal Bloom’ initiative). | 3.1.2.1 Identify how to best package EW information in user-friendly format through surveys with the general public, and with specific targeted vulnerable groups/sectors in each country. 3.1.2.2 Train stakeholders in identified best dissemination channels for the general public and for the targeted groups (e.g. radio/TV presentations/community leaders) will be trained to disseminate warnings Responsible parties: communication consultant hired under 3.1.1 - Leader : IOC with the Support of PMU expertise to recruit a communication consultant - Beneficiary supervision and validation : NMHS, DRR and targeted sectoral institutions in each country - Stakeholders to be involved and consulted: NMHS, DRR institutions and population (for surveys) in each country | Strengthened EWS in each country |
| 3.2.1 Improve data sharing and coordination with emergency services for on-the-ground interventions at national and local levels | Strengthening the collaboration between NMHS and DRR institutions was a recommendation identified in Annex 2, the FS, Chapter 4. Such collaboration will be fostered in the four countries under this project’s (see Activity 1.2.1). Through case studies, the FS has also underlined problems linked to disaster risk management in the four countries (see SWOT analysis, Annex 2, the FS, Chapter 3); it underlines in 2 vulnerable areas, will demonstrate how to downscale national emergency response plans at the local level to improve risk prevention, mitigation and recovery, in order to be replicated in other vulnerable sites. | Sub-activities 3.2.1.1 Working with NMHS, DRR institutions and emergency services, identify pathways to improve communication and coordinate interventions among these services 3.2.1.2. Conduct local assessment of on-the-ground intervention organisations including local community leaders, red cross/crescent, NGOs in 2 pilot sites per country 3.2.2.3 Update national and develop local emergency response plans working in partnership with DRR institutions, emergency response services and local stakeholders 3.2.2.4 Train local stakeholders in the selected pilot sites on risk prevention, mitigation and recovery 3.2.2.5 Develop disaster risk reduction products – e.g. flyers in local languages, signs displayed and pictures – to place in strategic public spaces of the selected pilot sites to inform communities of DRR measures Responsible parties: - Leader : IOC with the Support of PMU expertise to recruit a DRR consultant - Beneficiary supervision and validation : DRR institutions and emergency services - Stakeholders to be involved and consulted: DRR institutions, emergency services and population (for surveys) in each country | National and local emergency response plans |
| 3.2.2 Update long term climate change adaptation plans responding to the needs of each country | Comoros, Madagascar and Mauritius are in the process of developing their NAP, which will be finalised in 2020. Based on the high-quality climate data and projections produced under Component 2 (in particular Output 2.3), the NAPs will be updated. In Seychelles, where no NAP is being developed, the project will support the implementation of the R&D component of the existing Coastal Management Plan (based on hazard maps developed under Activity 2.3.5) and update the national climate change strategy (in support to the new climate change policy to be validated in 2019). The plans will be shared on the UIP (Activity 3.3.3). | 3.2.2.1 Update NAPs in Comoros, Madagascar and Mauritius 3.2.2.2 In Seychelles, work with the Climate Change Department to implement the CMP and update the national climate change strategy Responsible parties: - Leader : IOC with the Support of PMU expertise to recruit a climate change adaptation consultant - Beneficiary supervision and validation : Ministry of Environment/ climate change units; relevant sectoral ministries (e.g. agriculture) Stakeholders to be involved and consulted: Ministry of Environment/ climate change units; relevant sectoral ministries (e.g. agriculture) | Updated NAPs and climate change strategies |
| 3.3.1 Train staff members of NMHS and in the RCC on how to package climate-related information in a user-friendly way | Workshops with NMHS and CP-CS users in priority areas of the GFCS will be organised to ensure better packing of climate-related products prepared by the NMHS including sector-tailored forecasts and EW. At least 15 members of each NMHS will be trained. | 3.3.1.1 Develop training programme on packaging and communicating climate-related information 3.3.1.2. Identify stakeholders within key institutions of provider and user of CP-CS to invite at workshop 3.3.1.3 Organise workshops to facilitate discussions between producer and users of CP-CS and identify ways to package CP-CS so that they are understandable and useful. Responsible parties: - Leader : IOC with the Support of PMU expertise and communication consultant hired under Activity 3.1.1 - Beneficiary supervision and validation : NMHS and CP-CS users Stakeholders to be involved and consulted: NMHS, DRR institutions and relevant sectoral organisations |  |
| 3.3.2 Train knowledge brokers – including NGOs, red crescent/cross, local leaders and extension officers – and representatives of sectors in the GFCP-CS areas (public and private organisations) on how to interpret and use CP-CS for decision-making | Key knowledge broker institutions for risk prevention and response at the local level will be identified in each country. Their capacity to understand risk warnings and alerts, to provide accurate advices on risk prevention and to react during/after a hazard will be strengthened through trainings. | 3.3.2.1 Identify local ‘knowledge brokers’ in risk prevention 3.3.2.2 Develop a training programme for knowledge brokers on how to interpret and use CP-CS for decision-making 3.3.2.3 Organise a workshop to train knowledge brokers 3.3.2.4 Prepare and disseminate knowledge material (also on the UIP) Responsible parties: - Leader : IOC with the Support of PMU expertise and communication consultant hired under Activity 3.1.1 - Beneficiary supervision and validation : DRR institutions Stakeholders to be involved and consulted: DRR institutions and knowledge brokers |  |
| 3.3.3 Strengthen the User Interface Platform (UIP) | The project will strengthen the existing Regional Climate Portal developed by IOC and hosted by Seychelles (SMA) since August 2019. The platform, which is regional and will be a key communication tool for the RCC (see Activity 1.1.2), is already used by MF and IOC to disseminate climate-related information following SWIOCOF. Through Hydromet project, the platform will serve to facilitate access to CP-CS (weather bulletin, seasonal forecasts, alerts, climate change projects and vulnerability assessments), including those produced during SWIOCOF and NCOF, within and between countries. The products developed under Output 2.3 – the climate-related hazards maps and vulnerability maps – will also be shared on the platform, as well as the updated, downscaled climate change projections produced under the same Output. The platform will target stakeholders working in the GFCP-CS priority areas (from public and private sectors, e.g. ministries, business, researcher, etc.) to provide them with decision-making support tools or with climate-related information that can be used to produce targeted CP-CS. For this purpose, the information will be packaged according to their needs. The platform will be designed to include a page where users of CP-CS can provide feedback on the services they receive (Annex 2, the FS, Chapter 3 has identified a lack of feedback loop between NMHS and users of climate services). | 3.3.3.1 Identify gaps/weaknesses in the design/operationalisation of the existing Regional Climate Portal. 3.3.3.2 Conduct interviews with users of the platform to identify gaps/weaknesses in information provided (packaging, content, ‘usability’) 3.3.3.3 Develop and implement a communication strategy to improve the platform which include tool to collect users’ feedback on CP-CS. Responsible parties: - Leader : IOC with the Support of PMU expertise and communication/IT consultant hired under Activity 3.1.1 - Beneficiary supervision and validation : RCC, NMHS, CP-CS users - Stakeholders to be involved and consulted: meteorological services and platform users | 1 strengthened regional UIP |
| 3.3.4 Support SWIOCOF to ensure the active participation of climate services users | SWIOCOF is a yearly event convened by IOC (September). Its efficiency will be assessed by a meteorologist expert and recommendations will be made to improve its impact, in particular to enhance its complementarity with NCOF/SARCOF. This assessment will seek to assess SWIOCOF so it can provide CP-CS users with relevant and action-oriented seasonal information; and offer a platform for users to provide feedback on CP-CS including early warning systems (improvement to be made based on assessment of existing process in SWIOCOF). The lessons learned collected from users will be shared on the online platform from Activity 3.3.3. To note that a funding strategy to maintain SWIOCOF beyond the proposed project’s lifetime will be developed under Activity 1.2.1. | 3.3.4.1 Conduct capacity gap analysis on SWIOCOF to identify pathways for improvements 3.3.4.2. Identify how to best complement SARCOF and NCOFs 3.3.4.3 Design a strategy for IOC to improve SWIOCOF with a view to enhance users’ implication in the forum. Responsible parties: - Leader : IOC with the Support of PMU expertise to recruit a meteorologist expert - Beneficiary supervision and validation : IOC/RCC, CP-CS users Stakeholders to be involved and consulted: SWIOCOF participants | Strengthened SWIOCOF |

E.7. Monitoring, reporting and evaluation arrangements (max. 500 words, approximately 1 page)

Monitoring, reporting and evaluation arrangements will comply with the relevant GCF policies. Reporting to the PMU The EE, through its PMU, will ensure the day-to-day monitoring and overseeing project implementation, ensuring coordination with relevant partners including NPCs, NFPs, NMHSs and NDAs, exchanging with local government, etc. Every semester, the PMU will review project performance and assess any potential risks. This task will be performed by the Monitoring and Evaluation (M&E) Officer member of the PMU, with the assistance of the four national Project Focal Point (NFP) and (NPCs). The RPC will visit projects sites at least once a year; and more if deemed necessary. NPCs will liaise continuously with the RPC. At the national level project implementation report will be prepared by the NPCs on a biannually basis, based on this; the RPCs will monitor the implementation progress and adjust the annual work plan and objectives. At the end of the disbursement period, the EE will prepare a project completion report summarising the main events of the implementation phase, the results achieved, and the lessons learned. This report will also provide recommendations for future improvements. Reporting to the AE During the disbursement period, AFD will receive reports from the EE, i.e. the IOC, to track progress and identify potential issues as well as improvement opportunities. In this document, the EE will report on a semi-annual or annual basis on performance indicators; these indicators will be detailed in a result monitoring framework developed to assess progress towards the Project Development Objective (PDO) through key indicators; while intermediate indicators will monitor the progress of each component over the life of the Project. Accounting and financial audits will also be conducted every year by AFD and/or an independent third party. AFD will tender and contract an independent consultancy services for the mid-term review (MTR) and for the ex-post evaluation of the project after its full completion for a terminal evaluation (TE). The MTR and TE aim to improve future project implementation as well as other projects/programmes by deriving lessons from experience and to find ways to make aid more effective. Reporting to the GCF Annual Performance Reports (APR) will be duly prepared by AFD and shared in a manner compliant with the provisions of the Accreditation Master Agreement (AMA), the Funded Activity Agreement (FAA) and the Monitoring and Accountability Framework (MAF) of GCF. In particular, the APR may include a narrative report on the implementation progress based on the logical framework, considerations on the ongoing performance of the proposed project, updates on the indicators, and a report on environmental and social safeguards (ESS) as well as gender issues.

| # RISK ASSESSMENT AND MANAGEMENT |  |  |
| --- | --- | --- |
| F.1. Risk factors and mitigations measures (max. 3 pages) |  |  |
| Selected Risk Factor 1 |  |  |
| Category | Probability | Impact |
| Technical and operational | Medium | High |
| Description |  |  |
| Project implementation could be affected by the limited capacity among NMHSs to operationalise the new/upgraded hydro-meteorological equipment and to implement project. This could happen if: i) NMHSs do not appoint appropriate experts to operationalise equipment, or do not provide adequate training to their staff members; ii) Staff members of the meteorological and hydrological services are not involved in project implementation; or iii) Operation and maintenance costs during and after project cannot be met by the NMHSs. |  |  |
| Mitigation Measure(s) |  |  |
| These risks will be mitigated through the following project interventions: i) the signature of memorandum of understanding between the EE and the national counterpart of beneficiary country to confirm their involvement and means commitment, ii) institutional and technical capacity of beneficiary NMHSs will be strengthened to improve their operationalisation and retain skilled staff; staff will also be trained to operationalise equipment and new staff will be hired (as needed), to enable effective project implementation and coordination; iii) the project has been designed in consultation with the NMHSs of each beneficiary country, which will be involved in project implementation at the national level; indeed, a National Focal Point (NFP) will be appointed within the NMHS to ensure collaboration and involvement of these services during project implementation; the NMHSs will also be represented during bi-annual national project steering committees and annual regional steering committee to ensure their commitment and engagement; and iv) modernization of key equipment and training on their operation and maintenance will support increased capacity for project implementation among the beneficiary NMHSs during and after the project; moreover, a calibration center will be established for the SWIO region to facilitate the maintenance and calibration of hydro-meteorological equipment; finally, as indicated in the Economic Analysis (Annex 3a), financial capacity of the NMHSs would increase through the production and sale of high-quality CP-CS, hence additional financial resources will be reinvested into operation and maintenance after project implementation. |  |  |
| Selected Risk Factor 2 |  |  |
| Category | Probability | Impact |
| Governance | Medium | High |
| Description |  |  |
| The proposed project could be affected by a limited commitment of the government towards project implementation; for example, new appointments in the government – ministries or NMHS – could affect project implementation in the country. |  |  |
| Mitigation Measure(s) |  |  |
| The risk is more significant in politically-instable countries, prone to government re-shuffle. To ensure strong involvement of the beneficiary countries, extensive in-country consultations – with representatives of the NMHSs, relevant line ministries, and NDAs – were conducted during the project development phase. Two series of workshops were held (at national and regional level) to provide opportunities for countries to comment and adjust requirements. As such, expectations from NMHSs and CP-CS users have been incorporated where relevant to ensure greater buy-in. NPC will also be appointed within the NMHS to coordinate project implementation in their country. In addition, IOC will sign bilateral agreements with each Ministry of Foreign Affairs, which, in turn, will sign agreements with the line ministry of the meteorological services in the four target countries. This will serve to ensure that NMHS remain in charge of national project implementation (through their NPC), even if changes occur at the head of the parent ministry. |  |  |
| Selected Risk Factor 3 |  |  |
| Category | Probability | Impact |
| Technical and operational | Low | Low |
| Description |  |  |
| Security issues and vandalism put hydro-meteorological equipment at risk of damage or loss. Tensions with the population located where the new hydro-meteorological equipment will be installed could rise especially if population relocation is necessary; this could result in damages caused by the impacted population to the equipment. |  |  |
| Mitigation Measure(s) |  |  |
| Several actions will be undertaken to avoid relocating population, engage with the population located nearby hydro-meteorological equipment and ensure the equipment is not damaged during and after project implementation: No relocation is foreseen within this project: most equipment will be set up or upgraded in sites already used by such equipment and building extension/construction (for the meteorological services in Comoros and Seychelles) will take place on land already acquired by the meteorological services; Communities surrounding the newly established/upgraded equipment will be informed beforehand of the purpose of the project and type of equipment to be installed; The equipment will be equipped with argos tracking tags, whenever possible; Fences will be set up around the equipment; Awareness-raising of the benefits of CP-CS will be conducted so that the communities appreciate the value of the hydromet equipment installed nearby; and Agreements will be signed with the NMHS or their line ministry of the 4 countries to protect the equipment during their lifetime (e.g. equipment insurance where possible). |  |  |
| Selected Risk Factor 4 |  |  |
| Category | Probability | Impact |
| Technical and operational | Medium | Medium |
| Description |  |  |
| There is a risk that climate-related hazards will damage the hydro-meteorological equipment during and after the project lifetime. For example, tropical cyclones and storms could destroy automatic weather stations and communication infrastructure if those are not carefully placed using resilient material. |  |  |
| Mitigation Measure(s) |  |  |
| The four beneficiary countries are affected by climate-related hazards which could cause damages to the newly established equipment. Particular attention will be given to site selection to install new equipment in ‘risk-free’ areas – e.g. avoiding low-land areas affected by floods. This will, for example, be ensured by installing the new equipment in similar location of previously set equipment if this location is known for not being affected by climate extremes. In addition, all infrastructure and equipment will be built with adequate construction materials and efficient design to be resilient to severe and frequent tropical cyclone events, floods, high winds etc (future-proof). Finally, enhanced climate-related risk prediction will enable the NMHSs to protect or remove movable equipment when a risk alert is launched. |  |  |

# GCF POLICIES AND STANDARDS

G.1. Environmental and social risk assessment (max. 750 words, approximately 1.5 pages)

The proposal for Hydromet is predominantly one of capacity building and institutional strengthening to deliver improved climate services. There will be an associated provision of new meteorological equipment for monitoring, measurement and data storage and sharing systems. These are specified in relation to both the needs of each country and requirements for coordinated IOC regional climate services provision. This component of the project encompasses the refurbishment and re-equipping of existing weather stations and installation of strategically-placed weather monitoring equipment facilities and river gauges, etc. Such state of the art technology will record meteorological and hydrological data to be analysed and disseminated to government services and end users, including the general public. Environmental and social risks As evaluated in the assessment, the project is expected to have minimal environmental and social impacts and is more likely to generate beneficial impacts. The project has been classified overall as Category B. The safeguards risks are primarily associated with the installation of new meteorological equipment mounted on masts (e.g. new or rehabilitated automatic weather stations, AWS), or in the case of the Doppler Radar units on small tower structures (also supplied will be work stations, computers, wiring, etc.). AWSs are typically installed within local government owned properties. A very limited area is required for each weather station (some 50-100m2) at sites of modified and semi-natural habitat, such as airfields or government research institutes. With the exception of river gauges, the equipment will be installed almost exclusively at existing stations where they can be protected from damage, being on secure premises and/or through secure fencing. Many stations have fallen into disuse and project meteorological equipment will be established on existing sites on government-owned land; therefore, the project will not result in land acquisition and/or resettlement of local population. It is anticipated that there will be minimal planning requirements but following the environmental planning procedure of the ESMF all local permitting requirements will be adhered to and the PMU will facilitate and assure such regulations are respected and ESMF plan reporting requirements will enable monitoring and accountability. In each of the countries it is anticipated that one Doppler Radar unit will be installed and these will be mounted on a base or tower (up to some 8 metres in height). There will also be a small number of wave-monitoring buoys and tidal gauges. Modification and extension of existing buildings associated with offices and weather station facilities is also envisaged. The Seychelles government are relocating their main offices at their own expense and these will receive certain project supplied computers and data processing equipment. Potential negative environmental and social impacts which would potentially occur from the installation works of AWSs include noise pollution from machinery and equipment, increase in generation of solid wastes, and increase in dust emissions as a result of excavation and civil works during the installation of the AWSs especially in new sites. These impacts will affect, albeit temporarily, occupational health and safety of workers to be involved during construction works and surrounding localities in close proximity to the selected local government owned properties. The ESMF (E&S framework) has examined all such potential impacts and suggests negligible potential impacts if basic codes of good health and safety practice are followed by contractors, including national and international regulations applicable in the countries including ILO conventions. The nature of the project is such that its potential physical impact and safeguards risk factor is necessarily limited. The new physical infrastructure element at any location will be very modest in size and dispersed in siting so cumulative issues are not a relevant consideration. Environmental Management The process of optimal site selection for facilities is addressed together with health and safety guidance for construction. Planning requirements for Doppler Radar installations and the wave height monitoring buoys will respect national planning compliance expectations. The construction safeguards are not only relevant to installation works but also any protection fencing to guard against third party damage. A “fit-for-purpose” approach is adopted in line with the GCF risk-based policy to the project proponent and guide management and monitoring of sub-contractors. The project will ensure that all equipment to be purchased meets international environmental, safety and technical standards. Where there are alternative options in siting the proponent will seek the optimal location subject to approval of the national environmental authorities. An E&S safeguards monitoring and reporting component will constantly review and audit the implementation of the programme including setting up of new and rehabilitated weather stations to verify that safeguards are implemented. In conclusion, very limited negative risks are predicted to arise from the project and, when effectively implemented, the project will provide reliable climate data of importance for climate risk adaptation and enhancing the management of natural resources, mitigating vulnerability of exposed populations and assets to climate change. Some sites will benefit positively as buildings and station sites in poor condition are renovated resulting in positive direct and indirect impacts. The accompanying training in use of new project-supplied equipment will include health and safety in equipment and facility use. The ESMF (see Annex 6) presents actions to assure sound safeguards implementation to manage risks and achieve compliance with national and IFC requirements, and therefore realise the significant benefits of the project while avoiding or mitigating any adverse effects.

G.2. Gender assessment and action plan (max. 500 words, approximately 1 page)

The proposed GCF project includes a Gender Assessment and Action Plan (Annex 8). The analytical prerogatives of the Gender Assessment and Action Plan are informed by both GCF and AFD gender policies: the 2018 Gender Policy and Action Plan passed by the GCF (building upon the 2014 edition); and, the AFD Strategy on Gender and the Reduction of Gender Inequalities (2014) as well as its AFD Group Strategy 2018 – 2022. There is no gender strategy available currently at IOC level. However, national gender plans are available in each of the four countries. These plans were reviewed along with other gender-related legislations such as on economic empowerment and prevention of gender-based violence, and with gender-related protocols like the CEDAW and Maputo protocols. These serve to point out the national legal and institutional frameworks and the gender priorities of each country, which can be used to support gender equality through the proposed project. The proposed Gender Assessment provides an overview of the gender baseline in each beneficiary country (alongside a regional appraisal). The assessment is based on a rapid in-country missions as well as desk-review of available secondary literature and data. Particularly, the assessment identifies key gender-related factors that determine climate resilience, access to EWS and CS, potential inequality aspects and trickle-down effect of project benefits towards end-users of CP-CS (most particularly within vulnerable communities). Semi-structured interviews (with focus groups, key informants, and institutional representatives) were conducted during short in-country missions. A comprehensive literature desk-review was conducted on gender, climate change adaptation, climate services and hydro-meteorological services. The triangulated assessment was synthesised to cover the four project countries, taking into consideration their unique contexts and performances and across social indicators. Gender-differentiated climate impacts and natural disasters: The World Economic Forum (WEF)’s report The Global Risks Report 2020 finds that the top five among the primary ten risk factors facing the world population are environmental in nature: (in order of risk) extreme weather, climate action failure, natural disasters, biodiversity loss, human-made environmental disasters. Gender determinants (such as consumption patterns and incidence of poverty, access to and control of resources and power, time use patterns and economic activities) when juxtaposed with environmental risks, can uniquely compound and overlap to create progressive vulnerabilities in each of the project countries. High burden of adverse impacts of climate change, especially with the lack of EWS, CS, and hydromet services, will limit not only adaptation capacities in real time, but also have intergenerational effects and undo progress made towards gender equality in the island nations (with increased consequences especially in LDC contexts of Madagascar and Comoros). Gendered access to adaptation solutions: Site visits undertaken in the Comoros (Moroni) and Seychelles (La Digue, Praslin and Victoria) and engagement with government officials in all four countries, revealed that adaptation solutions, ranging from DRR training to climate-resilient agricultural inputs, face gendered barriers. For the operationalisation of the IOC Hydromet project, it is important to consider that women are often not allowed to access public spaces (where EW may be announced – such as mosques in Comoros) or have limited to no radio access (in Madagascar), and generally, the dissemination of information are restricted to channels primarily accessed and controlled by men. Gendered limitations in decision-making institutions and representation: Decision-making institutions, power-sharing mechanisms and overall representation tend to be skewed towards men in all four IOC countries, barring Seychelles. Yet, at the same time, women make important household decisions daily, in these countries, that pertain to domestic food security, water provision, and other essentials – which contribute towards DRR response, resilience during extreme weather events, adaptation capacities. An adequate integration of these complex and gendered phenomena in the project approach will, thus, be necessary to respond to particular needs and interests of vulnerable groups at decentralised and grassroots locales. Bottom-up, tailored approach, will ensure project ownership, and sustainability at the community context. Side-lining local adaptation measures and information channels: Communities of the western Indian Ocean possess experience, history and knowledge in the management and use of natural resources as sustainable livelihood sources. Thus, self-help adaptation methods, particularly those discrete and reactive in nature – information channels, sharing of resources and communal control of wastage during crises, building strategies – can be traced among these communities. The project, especially due to its focus on building resilience of communities, as well as ecosystems, thus has to ensure the incorporation of these techniques into broader, pre-emptive EWS, CS and hydromet services. Such a process will require vetting as well as emphasis on cross-community dialogue to tailor these provisions, consider inclusions and exclusions, manage expectations, etc. Additionally, Annex 8 gives consideration to gender-based violence and time poverty experienced by women and men (in some contexts), and how these phenomena can also constrain the adoption of adaptation solutions, particularly in ex post disaster and other vulnerable contexts. In order to address the above-mentioned gendered limitations, particularly women’s participation in adaptation solutions, and to build on the potential opportunities of increased gender equality through the objectives and outputs of the IOC Hydromet project, a Gender Action Plan has been developed. Key actions included in the plan are presented in the table below per project component: Project Component; Gender Action Point. 1. Capacity Building, Institutional, Development and Regional Cooperation among NMHSs; - Include gender-responsive policy inputs in regional and national frameworks developed for climate services (with reference to WMO Gender Strategy) - Ensure gender capacity building through the design of training modules to assist transition and development plans of NMHSs, DRR institutions and relevant sectoral ministries - Increase gender parity in new staff and trainees hired for EWS, CS, and hydromet services. 2. High Quality Climate – related data and improved climate risk assessments and climate change projections.; - Ensure gender-engagement training of observers and forecasters, particularly those involved in impact forecasting and nowcasting, to increase gender-responsiveness of EWS and CS products - Research and include community and social vulnerabilities, particularly gendered impacts and gender-differentiated capacities of resilience, in the hazard maps and climate vulnerability maps developed for each country. 3. Enhance use of climate services for climate change adaptation and disaster risk reduction at national and regional level; - Conduct needs assessments to ensure gender-responsiveness of daily weather bulletins, seasonal forecasts and agricultural advisories - Ensure gender-responsiveness in EW dissemination, particularly the limited access women have to public spaces (mosques in Comoros), or information channels (radios in Madagascar), and the incidence of gendered time poverty.

G.3. Financial management and procurement (max. 500 words, approximately 1 page)

Contracting Authority AFD will sign a subsidiary agreement with the IOC, representing the beneficiary country. This agreement and the related documents will specify the tasks related to IOC and beneficiary countries. For the implementation of the Project the IOC (EE) will also sign a Memorandum of Understanding (MoU) with the Ministry of Foreign Affairs (MoFA) of Beneficiary countries. At National level each MoFA will also sign a Memorandum of Understanding (MoU) with line ministries of the national meteorological and hydrological services or with the concerned Agencies directly such as for Seychelles and Comoros. These MoUs aim at clarifying the mandates, roles and commitments of each party. Procurement AFD’s Procurement rules are in line with international standards provided by the World Bank Group. The AFD Procurement guidelines will apply to the EE, in charge of implementing the Programme. For a detailed presentation of AFD Procurement rules, see the Procurement Guidelines for AFD Financed Contracts in Foreign Countries available on AFD’s website (https://www.afd.fr/sites/afd/files/2017-09/directives-passation-marches-etats-etrangers-english-version.pdf). AFD supervision of the project AFD will provide no –objections : - Prior to the signing of the MoU between EE and MoFA and MoU between MoFA and National line ministries or beneficiary entities , - On semi-annual national reporting Progress Reports, and on annual technical and financial work plan prepared by the PMU, - On every steps of a tendering process according to its own procedures Bi annual supervisions missions will take place; including mobilization of headquarters expertise. Environmental, social and gender AFD expert staff could be assigned to the monitoring of the ESMP and Gender Action Plan. Financial Management The detailed provisions regarding financial management of the GCF resources by AFD will be described in the Funded Activity Agreement (FAA) signed between GCF and AFD. Reporting will be provided by AFD to the GCF specifying among others: 1) the amounts already committed and disbursed by AFD to the EE; 2) the remaining amount; and iii) a provisional disbursement schedule on a one-year rolling horizon. Annual Performance Reports (APR) will be submitted to GCF following the reporting requirements detailed in the FAA. These reports will include a narrative on the implementation progress based on the logical framework, considerations on the ongoing performance of the project, updates on the indicators, and on ESS as well as gender. The APR will be submitted to the Secretariat on an annual basis for the period ending on 31 December within 60 days after the end of the relevant annual period. The first APR will be submitted following the end of the calendar year after the Parties have entered into the relevant FAA and the last APR will be submitted within six months of the end of the relevant reporting period. The implementation reporting period of the Project will start from the date of effectiveness of the FAAs until the project implementation end date. Mid-term and final independent evaluation of the project will be organised. Accounting and disbursements The subsidy agreement to be signed between AFD and IOC will establish the terms and conditions of the cooperation and define clear roles and responsibilities for both parties. The details of contracts and flow of funds will be agreed upon through this convention. As the AE, AFD will disburse funding received from the GCF and the EU, EE must open a separate bank account for the project; this ensures transparency regarding financial transactions and renders audits more efficient. The EE, with the support of the PMU; will be the manager of the revolving advance project account. Revolving Advance payments will be made by AFD at the request of IOC, based on the issuance of activity reports and according to the disbursement schedule of the convention. The advance payments tranches will be used to for : - signed services contacts with n maximum amount of ten thousand dollars (10,000 USD), - payment of PMU members staff and PMU set-up and running costs. Each request to be introduced by the EE for a new advance payment drawdown should be accompanied by the necessary proof of consumption of funds from the previous advance tranches (70% of the previous (N-1) and 100% of the advance (N-2) and all other relevant documents and services contracts. For all contract providers of goods and services with an amount superior to ten thousands euros (10,000 €), direct payments will be covered by AFD. As IOC is in the process of acquiring GCF accreditation, it will benefit from capacity development in the project from acting as EE. During the disbursement period, AFD will receive semi-annual reports from IOC on implementation to track progress and identify potential issues as well as improvement opportunities. The RPC will liaise with AFD every quarter to report on project implementation. AFD will also be represented at the Project Regional Steering Committee organised every year. Controls will be performed before every disbursement by the PMU Financial Officer so as to continuously oversee the correct implementation of the project. Accounting and financial audits will be conducted by AFD and/or an independent third party. At the end of the disbursement period, AFD will prepare a project completion report summarising the main events of the implementation phase, the results achieved, and the lessons learned. This report will also provide recommendations for future improvement. Cash Flow The figure below depicts the flow of funds between IFIs, the AE, the EE and the providers of services, goods and equipment. Figure 3: Flow of Funds

G.4. Disclosure of funding proposal

☒ No confidential information: The accredited entity confirms that the funding proposal, including its annexes, may be disclosed in full by the GCF, as no information is being provided in confidence. ☐ With confidential information: The accredited entity declares that the funding proposal, including its annexes, may not be disclosed in full by the GCF, as certain information is being provided in confidence. Accordingly, the accredited entity is providing to the Secretariat the following two copies of the funding proposal, including all annexes: - full copy for internal use of the GCF in which the confidential portions are marked accordingly, together with an explanatory note regarding the said portions and the corresponding reason for confidentiality under the accredited entity’s disclosure policy, and - redacted copy for disclosure on the GCF website. The funding proposal can only be processed upon receipt of the two copies above, if containing confidential information.

| # ANNEXES |  |  |  |  |
| --- | --- | --- | --- | --- |
| H.1. Mandatory annexes |  |  |  |  |
| ☒ |  | Annex 1 |  | NDA no-objection letter(s) (template provided) |
| ☒ |  | Annex 2 |  | Feasibility study - and a market study, if applicable |
| ☒ |  | Annex 3 |  | Economic and/or financial analyses in spreadsheet format |
| ☒ |  | Annex 4 |  | Detailed budget plan (template provided) |
| ☒ |  | Annex 5 |  | Implementation timetable including key project/programme milestones (template provided) |
| ☒ |  | Annex 6 |  | E&S document corresponding to the E&S category (A, B or C; or I1, I2 or I3): (ESS disclosure form provided) ☐ Environmental and Social Impact Assessment (ESIA) or ☐ Environmental and Social Management Plan (ESMP) or ☐ Environmental and Social Management System (ESMS) ☐ Others (please specify – e.g. Resettlement Action Plan, Resettlement Policy Framework, Indigenous People’s Plan, Land Acquisition Plan, etc.) |
| ☒ |  | Annex 7 |  | Summary of consultations and stakeholder engagement plan |
| ☒ |  | Annex 8 |  | Gender assessment and project/programme-level action plan (template provided) |
| ☐ |  | Annex 9 |  | Legal due diligence (regulation, taxation and insurance) |
| ☐ |  | Annex 10 |  | Procurement plan (template provided) |
| ☐ |  | Annex 11 |  | Monitoring and evaluation plan (template provided) |
| ☐ |  | Annex 12 |  | AE fee request (template provided) |
| ☐ |  | Annex 13 |  | Co-financing commitment letter, if applicable (template provided) |
| ☐ |  | Annex 14 |  | Term sheet including a detailed disbursement schedule and, if applicable, repayment schedule |
| H.2. Other annexes as applicable |  |  |  |  |
| ☐ |  | Annex 15 |  | Evidence of internal approval (template provided) |
| ☐ | Annex 16 |  | Map(s) indicating the location of proposed interventions |  |
| ☒ | Annex 17 |  | Multi-country project/programme information (template provided) |  |
| ☐ | Annex 18 |  | Appraisal, due diligence or evaluation report for proposals based on up-scaling or replicating a pilot project |  |
| ☐ | Annex 19 |  | Procedures for controlling procurement by third parties or executing entities undertaking projects financed by the entity |  |
| ☐ | Annex 20 |  | First level AML/CFT (KYC) assessment |  |
| ☐ | Annex 21 |  | Operations manual (Operations and maintenance) |  |
| ☒ | Annex 22 |  | HYCOS Feasibility Study 2019 |  |

* Please note that a funding proposal will be considered complete only upon receipt of all the applicable supporting documents.

http://www3.weforum.org/docs/WEF_Global_Risks_Report_2019.pdf

https://www.gfdrr.org/en/power-of-partnership

South West Indian Ocean – Risk Assessment and Financing Initiative, 2017 (SWIO-RAFI)

AIR Worldwide, South West Indian Ocean Risk Assessment and Financing Initiative (SWIO-RAFI)

WGI AR5 Chapter 14; Table 29-1

https://www.worldbank.org/en/news/feature/2015/12/04/building-madagascars-climate-resiliency-to-ensure-food-security-and-preserve-livelihoods

https://www.ipcc.ch/srocc/

https://www.worldbank.org/en/region/afr/brief/hydromet-in-africa

Refer to Feasibility Study Annexes for the beneficiary calculations

World Bank, 2017. ‘South West Indian – Risk RAFI https://www.gfdrr.org/sites/default/files/publication/116342-WP-PUBLIC-52p-SWIO-RAFI-Summary-Report-2017-Publish-Version.pdf

WGI AR5 Chapter 14; Table 29-1; Nematchoua et al. (2018). A detailed study of climate change and some vulnerabilities in the Indian Ocean: A case of Madagascar island. Sustainable Cities and Society, vol. 41, pp.886-898

AIR Worldwide, South West Indian Ocean Risk Assessment and Financing Initiative (SWIO-RAFI), Final Report Submitted to the WBG,

World Bank, 2017. ‘South West Indian – RAFI  https://www.gfdrr.org/sites/default/files/publication/116342-WP-PUBLIC-52p-SWIO-RAFI-Summary-Report-2017-Publish-Version.pdf

IOC Climate Change Portal. ‘Document cadre pour la stratégie régionale d’adaptation au changement climatique des pays membres de la Commission de l’océan Indien 2012-2020’. Accessed 18th August 2019.: https://prodigious-lab.com/coi/wp-content/uploads/2018/01/DR-Document-cadre-pour-la-strate%CC%81gie-re%CC%81gionale-d_adaptation-au-changement-climatique-des-pays-membres-de-la-COI.pdf

http://regionalclimate-change.sc/en/

https://www.worldbank.org/en/programs/africa_hydromet_program

https://public.wmo.int/en/resources/bulletin/alliance-hydromet-development

https://hydrohub.wmo.int/en/world-hydrological-cycle-observing-system-whycos

http://rcc.cimh.edu.bb/

http://www.wmo.int/pages/prog/wcp/wcdmp/CDM_2.php

Bapon S.H.M. Fakhruddin and Lauren Schick, 2019, “Benefits of economic assessment of cyclone early warning systems - A case study on Cyclone Evan in Samoa”, in Progress in Disaster Science

See p.12 of WMO’s Manual on the Global Data-processing and Forecasting System, 2010: https://www.wmo.int/pages/prog/www/DPFS/documents/485_Vol_I_en.pdf

The proposed interventions are based on missions in the four beneficiary countries; they also take into account the recommendations of HYCOS feasibility study which was conducted in June-September 2019.

See Annex 3a, Economic analysis and approach for a business plan.

http://www.wmo.int/pages/prog/wcp/wcasp/rcc/rcc.php

The proportion was calculated using the highest percentage for people having access to one of these communication means.

Given the size of Madagascar, the assumption is that the agricultural advisories and safety at sea alerts will reach 30% of the poplation involed in these sectors.

Ministry of Rural Development, Fisheries, Handicraft and Environment (2006). ‘Union of the Comoros: National Action Programme of Adaptation to climate change’. Accessed 19th August 2019. Available at: https://www.preventionweb.net/files/8507_com01e.pdf

Ibid. at page 6.

For Comoros, data extracted from : Rapport ACCLIMATE (2011). ‘Etude de vulnerabilite aux changements climatiques: evaluation qualitative’. For Madagascar, data extracted from : http://www.foodsecurityportal.org/madagascar/resources. For Mauritius and Seychelles, data extracted from : https://www.who.int/nutrition/publications/foodsecurity/state-food-security-nutrition-2019-en.pdf?ua=1

http://www.wmo.int/pages/prog/wcp/wcasp/rcc/documents/WCASP80_TD1534.pdf

http://regionalclimate-change.sc/en/

GCF – Green Climate Fund (2018). Updated Gender Policy and Action Plan. Policy Document. 
Accessed 22 April 2019. Available at: https://www.greenclimate.fund/documents/20182/1087995/GCF_B.20_07_-_Updated_Gender_Policy_and_Action_Plan_2018_2020.pdf/9bd48527-6e35-a72a-2f52-fd401d16d358

AFD – Agence Française de Développement (2019). Official Website. Accessed 2 August 2019. Available at: https://www.afd.fr/en/page-thematique-axe/gender-equality

However, it should be noted that Seychelles has put a GCF Readiness proposal together, which request the development of a regional IOC strategy for equal woman involvement in environmental projects. See GCF (2017). Readiness Proposal with the Indian Ocean Commission (IOC) for Republic of Seychelles. Project Document.

Comoros : National Policy on Gender Equality and Equity (2008)

Madagascar : National Policy for the Promotion of Women (2000 – 2015)

Mauritius : National Gender Policy Framework (2008)

Seychelles : National Gender Policy (2016)

World Economic Forum – WEF (2020). Official Website. Accessed 17 January 2020. 
Available at: http://www3.weforum.org/docs/WEF_Global_Risk_Report_2020.pdf

An individual is time poor if he/she is working long hours and is also monetary poor, or would fall into monetary poverty if he/she were to reduce his/her working hours below a given time poverty line. Thus being time poor results from the combination of two conditions (source: World Bank elibrary)